## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Jaypur | Bankura Division | Ghagara Piped Water Supply Scheme | SM/12426 | New | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 23/03/2023 | MABCO CONSULTANT | 15.12 | 1.08 | 7.14 | 30
2 | BANKURA | Jaypur | Bankura Division | Ghagara Piped Water Supply Scheme | SM/12426 | New | Material Requisition To Resource Division |  |  | RTOR000036/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 19.3 | 0 | 0 | 0
3 | BANKURA | Jaypur | Bankura Division | Ghagara Piped Water Supply Scheme | SM/12426 | New | Material Requisition To Resource Division |  |  | RTOR000298/2023-2024 | 884/BQA | 12/03/2024 | 12/03/2024 | Resource Division | 4.05 | 0 | 0 | 0
4 | BANKURA | Jaypur | Bankura Mechanical | Ghagara Piped Water Supply Scheme | SM/12426 | New | Ghagara Piped Water Supply Scheme |  |  | BILL/01497/2023-2024 | BP-23-24 -110 | 15/02/2024 | 15/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 14.38 | 0 | 0 | 0
Total | [13 empty] | 52.86 | 1.08 | 2.04