## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Jaypur | Bankura Division | Pankhai Piped Water Supply Scheme | SM/12427 | New | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Joypur Block under Bishnupur Sub-Division under Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/000219/2022-2023 | 1117/BQA | 18/05/2022 | 17/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 120.45 | 0 | 0 | 100
2 | BANKURA | Jaypur | Bankura Division | Pankhai Piped Water Supply Scheme | SM/12427 | New | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 23/03/2023 | MABCO CONSULTANT | 15.12 | 0 | 0 | 30
3 | BANKURA | Jaypur | Bankura Division | Pankhai Piped Water Supply Scheme | SM/12427 | New | Material Requisition To Resource Division |  |  | RTOR000076/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 55.83 | 0 | 0 | 0
4 | BANKURA | Jaypur | Bankura Mechanical | Pankhai Piped Water Supply Scheme | SM/12427 | New | Pankhai Piped Water Supply Scheme |  |  | BILL/01498/2023-2024 | BP-2023-24-103 | 15/02/2024 | 15/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.68 | 0 | 0 | 0
5 | BANKURA | Jaypur | Bankura Mechanical | Pankhai Piped Water Supply Scheme | SM/12427 | New | New service connection at Pankhai t/w-II ,hetia gp of joypur block under BMD PHE Dte. |  |  | BILL/00129/2024-2025 | BP-2024-25-37 | 10/05/2024 | 10/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.17 | 0 | 0 | 0
6 | BANKURA | Jaypur | Bankura Mechanical | Pankhai Piped Water Supply Scheme | SM/12427 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Pankhai Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000185/2025-2026 | 457/BMD | 10/06/2025 | 08/09/2025 | A.G.ENTERPRISE | 11.86 | 0 | 0 | 0
Total | [13 empty] | 214.11 | 0 | 0