## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of water supply scheme for Ashna (Katjuridanga) and adjoining mouzas | SM/12840 | Augmentation | Extention of HDPE Pipe line and installation of street stand post (SSP) at Samijinagar(Ghoshpara) and Madananaolly under Ashna (Katjuridanga) W/S Scheme under Bankura Sadar Sub -Division of Bankura division P.H.E.Dte. |  | Junior Engineer | ORD/000497/2022-2023 | 375/BQA | 23/02/2023 | 09/04/2023 | SUBHADIP DAS | 2.01 | 1.99 | 99.41 | 0
2 | BANKURA |  | Bankura Division | Augmentation of water supply scheme for Ashna (Katjuridanga) and adjoining mouzas | SM/12840 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2023-2024 | 1120/BQA | 12/05/2023 |  | Resource Division | 70.44 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation of water supply scheme for Ashna (Katjuridanga) and adjoining mouzas | SM/12840 | Augmentation | Soil Investigation work for construction of OHR (150 CUM CAPACITY) staging hight 20 mtr. under Augmentation of water supply scheme for Ashna (Katjuridanga) and adjoining mouzas under Bankura (Sadar) Sub - Division within Bankura Division, PHE Dte. (Zone- II) | Assistant Engineer |  | ORD/000637/2022-2023 | 576/BQA | 17/03/2023 | 01/04/2023 | MS G. MITRA AND ASSOCIATES | 0.68 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation of water supply scheme for Ashna (Katjuridanga) and adjoining mouzas | SM/12840 | Augmentation | . Preparation of DPR for Augmentation of water supply scheme for Ashna (Katjuridanga) and adjoining mouzas under Jal Jeevan Mission (JJM) Project of Bankura Sadar Sub - Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000153/2023-2024 | 1334/BQA | 01/06/2023 | 01/07/2023 | ENVIROTECH SOLUTIONS | 3.87 | 3.87 | 100 | 100
5 | BANKURA |  | Bankura Division | Augmentation of water supply scheme for Ashna (Katjuridanga) and adjoining mouzas | SM/12840 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000126/2023-2024 | 2732/BQA | 03/10/2023 |  | Resource Division | 6.22 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation of water supply scheme for Ashna (Katjuridanga) and adjoining mouzas | SM/12840 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000229/2023-2024 | 193/BQA | 22/01/2024 |  | Resource Division | 6.22 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Augmentation of water supply scheme for Ashna (Katjuridanga) and adjoining mouzas | SM/12840 | Augmentation | Augmentation of water supply scheme for Ashna (Katjuridanga) and adjoining mouzas under Bankura Sadar Sub - Division within Bankura Division, PHE Dte.(Zone- II) | Assistant Engineer | Junior Engineer | ORD/000398/2023-2024 | 2083/BQA | 27/07/2023 | 17/01/2025 | SANJOY PATRA | 298.83 | 13.2 | 4.42 | 11
8 | BANKURA |  | Bankura Division | Augmentation of water supply scheme for Ashna (Katjuridanga) and adjoining mouzas | SM/12840 | Augmentation | Augmentation of water supply scheme for Ashna (Katjuridanga) and adjoining mouzas under Bankura Sadar Sub - Division within Bankura Division, PHE Dte.(ZONE I) | Assistant Engineer | Junior Engineer | ORD/000338/2023-2024 | 1962/BQA | 18/07/2023 | 13/04/2024 | PRINCE INDUTRIES (INDIA) | 391.39 | 38.69 | 9.89 | 35
Total | [13 empty] | 779.66 | 57.75 | 7.41