## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Patrasayer | Bankura Division | Chandal Bandi Piped Water Supply Scheme | SM/13999 | New | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 25.37 | 0 | 0 | 0
2 | BANKURA | Patrasayer | Bankura Division | Chandal Bandi Piped Water Supply Scheme | SM/13999 | New | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 2011/BQA | 26/07/2024 | 26/07/2024 | Resource Division | 8.16 | 0 | 0 | 0
Total | [13 empty] | 33.53 | 0 | 0