## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Patrasayer | Bankura Division | Chandal Bandi Piped Water Supply Scheme | SM/13999 | New | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 25.37 | 0 | 0 | 0
2 | BANKURA | Patrasayer | Bankura Division | Chandal Bandi Piped Water Supply Scheme | SM/13999 | New | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 2011/BQA | 26/07/2024 | 26/07/2024 | Resource Division | 8.16 | 0 | 0 | 0
3 | BANKURA | Patrasayer | Bankura Mechanical | Chandal Bandi Piped Water Supply Scheme | SM/13999 | New | New service connection for Chandalbandi w/s scheme(T/W-I) at Patrasayer block under PHE Dte.(SM/13999) |  |  | BILL/01231/2024-2025 | BP-2024-25-307 | 09/12/2024 | 09/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 30.25 | 0 | 0 | 0
4 | BANKURA | Patrasayer | Bankura Mechanical | Chandal Bandi Piped Water Supply Scheme | SM/13999 | New | New service connection for Chandalbandi T/W-II watwer supply scheme (SM/13999) at Patrasayer block under BMD PHE Dte. |  |  | BILL/01207/2024-2025 | BP-2024-25-291 | 03/12/2024 | 03/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.5 | 0 | 0 | 0
5 | BANKURA | Patrasayer | Bankura Mechanical | Chandal Bandi Piped Water Supply Scheme | SM/13999 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & T/W No-II of Chandal Bandi piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Patrashayar, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000160/2023-2024 | 872/BMD | 04/05/2023 | 18/04/2026 | GOENKA ENTERPRISE | 35.78 | 16.49 | 46.1 | 46
Total | [13 empty] | 107.06 | 16.49 | 15.41