## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Patrasayer | Bankura Division | Atra Piped Water Supply Scheme | SM/14000 | New | Material Requisition To Resource Division |  |  | RTOR000073/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 53.82 | 0 | 0 | 0
2 | BANKURA | Patrasayer | Bankura Division | Atra Piped Water Supply Scheme | SM/14000 | New | Material Requisition To Resource Division |  |  | RTOR000011/2024-2025 | 2011/BQA | 26/07/2024 | 26/07/2024 | Resource Division | 13.1 | 0 | 0 | 0
3 | BANKURA | Patrasayer | Bankura Mechanical | Atra Piped Water Supply Scheme | SM/14000 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II of Atra Piped water supply scheme Block : Patrasayar under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000168/2023-2024 | 880/BMD | 04/05/2023 | 18/04/2026 | RAJIB COMPANY | 47 | 18.97 | 40.37 | 40
4 | BANKURA | Patrasayer | Bankura Mechanical | Atra Piped Water Supply Scheme | SM/14000 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Atra Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000026/2025-2026 | 237/BMD | 14/05/2025 | 12/08/2025 | M/S D. PALIT AND CO. | 11.66 | 0 | 0 | 0
Total | [13 empty] | 125.59 | 18.97 | 15.11