## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Patrasayer | Bankura Division | Salkhara Piped Water Supply Scheme | SM/14003 | New | Material Requisition To Resource Division |  |  | RTOR000054/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 19.11 | 0 | 0 | 0
2 | BANKURA | Patrasayer | Bankura Mechanical | Salkhara Piped Water Supply Scheme | SM/14003 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Shalkhara piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Patrasayer, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000029/2023-2024 | 656/BMD | 17/04/2023 | 14/10/2023 | P.K. ENGINEERING | 31.31 | 15.39 | 49.16 | 49
3 | BANKURA | Patrasayer | Bankura Division | Salkhara Piped Water Supply Scheme | SM/14003 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR SALKHARA PIPED WATER SUPPLY SCHEME, BLOCK- PATRASAYER, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000434/2023-2024 | 2268/BQA | 01/08/2023 | 31/05/2025 | PARAMESWAR CHOWDHURY | 285.23 | 58.47 | 20.5 | 36
Total | [13 empty] | 335.65 | 73.86 | 22