## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Patrasayer | Bankura Division | Mukundapur Piped Water Supply Scheme | SM/14006 | New | Material Requisition To Resource Division |  |  | RTOR000025/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 28.09 | 0 | 0 | 0
2 | BANKURA | Patrasayer | Bankura Division | Mukundapur Piped Water Supply Scheme | SM/14006 | New | Material Requisition To Resource Division |  |  | RTOR000303/2023-2024 | 884/BQA | 12/03/2024 | 12/03/2024 | Resource Division | 7.99 | 0 | 0 | 0
3 | BANKURA | Patrasayer | Bankura Mechanical | Mukundapur Piped Water Supply Scheme | SM/14006 | New | MUKUNDAPUR WATER SUPPLY SCHEME |  |  | BILL/01669/2023-2024 | BP-2023-24-185 | 22/03/2024 | 22/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.76 | 0 | 0 | 0
Total | [13 empty] | 47.84 | 0 | 0