## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Sonamukhi | Bankura Mechanical | Kubir Bandh Piped Water Supply Scheme | SM/14008 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Kubir Bandh piped water supply scheme (Zone- II) under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000028/2023-2024 | 655/BMD | 17/04/2023 | 14/10/2023 | UNITED TRADERS | 31.37 | 0 | 0 | 45
2 | BANKURA | Sonamukhi | Bankura Division | Kubir Bandh Piped Water Supply Scheme | SM/14008 | New | Material Requisition To Resource Division |  |  | RTOR000031/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 26.25 | 0 | 0 | 0
3 | BANKURA | Sonamukhi | Bankura Mechanical | Kubir Bandh Piped Water Supply Scheme | SM/14008 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Kubir Bandh piped water supply scheme (Zone-I) under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000427/2023-2024 | 1687/BMD | 27/07/2023 | 23/01/2024 | PRADIP KUMAR DHABAL | 36.76 | 0 | 0 | 53
4 | BANKURA | Sonamukhi | Bankura Mechanical | Kubir Bandh Piped Water Supply Scheme | SM/14008 | New | Kubir Bandh Piped Water Supply Scheme |  |  | BILL/01666/2023-2024 | BP-2023-24-183 | 22/03/2024 | 22/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.51 | 0 | 0 | 0
5 | BANKURA | Sonamukhi | Bankura Division | Kubir Bandh Piped Water Supply Scheme | SM/14008 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR CHAKAI & KUBIRBANDH PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000484/2023-2024 | 2336/BQA | 14/08/2023 | 09/05/2026 | PRINCE INDUTRIES (INDIA) | 1048.51 | 0 | 0 | 73
6 | BANKURA | Sonamukhi | Bankura Division | Kubir Bandh Piped Water Supply Scheme | SM/14008 | New | Balance Ancillary Work for ¿Kubirbandh¿ and ¿Chakai¿ Piped Water Supply Scheme, Sonamukhi Block, Bishnupur Sub Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000422/2025-2026 | 1989/BQA | 16/09/2025 | 15/03/2026 | PRINCE INDUSTRIES (INDIA) | 130.51 | 0 | 0 | 15
Total | [13 empty] | 1279.92 | 0 | 0