## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Sonamukhi | Bankura Mechanical | Pathara Piped Water Supply Scheme | SM/14009 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Pathra piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000159/2023-2024 | 871/BMD | 04/05/2023 | 31/10/2023 | INDRAJIT MITRA | 31.37 | 14.56 | 46.41 | 46
2 | BANKURA | Sonamukhi | Bankura Division | Pathara Piped Water Supply Scheme | SM/14009 | New | Material Requisition To Resource Division |  |  | RTOR000079/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 26.5 | 0 | 0 | 0
3 | BANKURA | Sonamukhi | Bankura Mechanical | Pathara Piped Water Supply Scheme | SM/14009 | New | New Service Connection for PATHRA TW-2(JL NO-153, PLOT NO-351)Water supply scheme under Bankura Mechanical Division PHE DTE |  |  | BILL/00010/2024-2025 | BP-2024-25-30 | 24/07/2024 | 24/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.35 | 0 | 0 | 0
4 | BANKURA | Sonamukhi | Bankura Mechanical | Pathara Piped Water Supply Scheme | SM/14009 | New | New Service Connection for PATHRA TW-1(JL NO-153 PLOT-689)Water supply scheme under Bankura Mechanical Division PHE DTE |  |  | BILL/00009/2024-2025 | BP-2024-25-29 | 10/06/2024 | 10/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.97 | 0 | 0 | 0
Total | [13 empty] | 79.2 | 14.56 | 18.38