## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Sonamukhi | Bankura Mechanical | Kalyanpur Piped Water Supply Scheme | SM/14010 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Kalyanpur piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000158/2023-2024 | 870/BMD | 04/05/2023 | 31/10/2023 | INDRAJIT MITRA | 31.37 | 0 | 0 | 46
2 | BANKURA | Sonamukhi | Bankura Division | Kalyanpur Piped Water Supply Scheme | SM/14010 | New | Material Requisition To Resource Division |  |  | RTOR000055/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 61.34 | 0 | 0 | 0
3 | BANKURA | Sonamukhi | Bankura Mechanical | Kalyanpur Piped Water Supply Scheme | SM/14010 | New | Kalyanpur Piped Water Supply Scheme |  |  | BILL/01513/2023-2024 | BP-2023-24-115 | 29/02/2024 | 29/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.69 | 0 | 0 | 0
4 | BANKURA | Sonamukhi | Bankura Division | Kalyanpur Piped Water Supply Scheme | SM/14010 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR KALYANPUR PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000098/2023-2024 | 1136/BQA | 15/05/2023 | 15/02/2024 | MD. AAMIR KHAN | 351.57 | 0 | 0 | 5
Total | [13 empty] | 447.96 | 0 | 0