## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Sonamukhi | Bankura Division | Patsol Piped Water Supply Scheme | SM/14011 | New | Material Requisition To Resource Division |  |  | RTOR000071/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 9.03 | 0 | 0 | 0
2 | BANKURA | Sonamukhi | Bankura Mechanical | Patsol Piped Water Supply Scheme | SM/14011 | New | New Service Connection for PATSOLE TW-1(JL NO-68, PLOT-159/188LR) Water supply scheme under Bankura Mechanical Division PHE DTE |  |  | BILL/00017/2024-2025 | BP-2024-25-27 | 10/05/2024 | 10/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.15 | 0 | 0 | 0
3 | BANKURA | Sonamukhi | Bankura Mechanical | Patsol Piped Water Supply Scheme | SM/14011 | New | New Service Connection for PATSOLE TW-2 (JL NO-68, PLOT-159/188) Water supply scheme under Bankura Mechanical Division PHE DTE |  |  | BILL/00024/2024-2025 | BP-2024-25-28 | 10/05/2024 | 10/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.58 | 0 | 0 | 0
4 | BANKURA | Sonamukhi | Bankura Mechanical | Patsol Piped Water Supply Scheme | SM/14011 | New | Acceptance cum Formal work order for the work of Providing & installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR at Patsol Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000062/2025-2026 | 401/BMD | 04/06/2025 | 02/09/2025 | S.DUTTA | 15.08 | 0 | 0 | 0
5 | BANKURA | Sonamukhi | Bankura Division | Patsol Piped Water Supply Scheme | SM/14011 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 31/12/2024 | MACKINTOSH BURN LIMITED | 13769.53 | 73.64 | 0.53 | 55
Total | [13 empty] | 13804.37 | 73.64 | 0.53