## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Indus,Kotulpur | Bankura Division | Patrabandh Piped Water Supply Scheme | SM/14012 | New | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Kotulpur Block under Bishnupur Sub-Division under Bankura Division, PHE Dte.. | Assistant Engineer |  | ORD/000220/2022-2023 | 1118/BQA | 18/05/2022 | 17/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 153.3 | 10.55 | 6.88 | 100
2 | BANKURA | Indus,Kotulpur | Bankura Division | Patrabandh Piped Water Supply Scheme | SM/14012 | New | Material Requisition To Resource Division |  |  | RTOR000065/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 57.78 | 0 | 0 | 0
3 | BANKURA | Indus,Kotulpur | Bankura Mechanical | Patrabandh Piped Water Supply Scheme | SM/14012 | New | New service connection at P/H-I at Patrabandh W/S scheme |  |  | BILL/00420/2024-2025 | BP-2024-25-100 | 21/06/2024 | 21/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.7 | 0 | 0 | 0
4 | BANKURA | Indus,Kotulpur | Bankura Mechanical | Patrabandh Piped Water Supply Scheme | SM/14012 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Pratapbandh Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000151/2025-2026 | 446/BMD | 10/06/2025 | 08/09/2025 | GOPAL CHANDRA CHOWDHURY | 11.84 | 0 | 0 | 0
Total | [13 empty] | 228.62 | 10.55 | 4.62