## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/B WATER SUPPLY SCHEME | SM/14091 | Augmentation | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-4B) (Sl. No. 08) |  | Junior Engineer | ORD/000324/2022-2023 | 186/KSD | 24/05/2022 | 08/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.43 | 3.43 | 100 | 0
2 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/B WATER SUPPLY SCHEME | SM/14091 | Augmentation | Construction of 5 mtr. x 5 mtr. size new Staff Room with allied Works for Mukutmanipur, Khatra & Ranibandh (Zone- V/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000576/2022-2023 | 445/BQA | 06/03/2023 | 04/06/2023 | MOHAMMAD HASAN KHAN | 8.64 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/B WATER SUPPLY SCHEME | SM/14091 | Augmentation | Construction of 5 mtr. x 5 mtr. size new Staff Room with allied Works for Mukutmanipur, Khatra & Ranibandh (Zone- IV/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000569/2022-2023 | 442/BQA | 06/03/2023 | 04/06/2023 | EDER ALI KHAN | 8.65 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/B WATER SUPPLY SCHEME | SM/14091 | Augmentation | Construction of Chlorine Room at OHR Site for Mukutmanipur, Khatra & Ranibandh (Zone- IV/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000571/2022-2023 | 443/BQA | 06/03/2023 | 04/06/2023 | SOMENATH ACHARYYA | 4.63 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/B WATER SUPPLY SCHEME | SM/14091 | Augmentation | Construction of Boundary Wall (Length- 130 Mtr.) with allied Works at Head Work site for Mukutmanipur, Khatra & Ranibandh (Zone- IV/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000572/2022-2023 | 444/BQA | 06/03/2023 | 20/04/2023 | SOMENATH ACHARYYA | 19.54 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/B WATER SUPPLY SCHEME | SM/14091 | Augmentation | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-4B of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000239/2023-2024 | 1124/BMD | 24/05/2023 | 23/06/2023 | M/S DAS & SARKAR ENTERPRISE | 2.39 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/B WATER SUPPLY SCHEME | SM/14091 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works, providing ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 250 m³ capacity R.C.C OHR(based on Departmental Design) with 20 mtr staging height including foundation, pipeline connection and cost of pipes, specials etc. with allied worksfor Mukutmanipur, Khatra & Ranibundh (Zone- IV/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000553/2023-2024 | 2364/BQA | 14/08/2023 | 10/05/2024 | MANJAR ALI KHAN | 407 | 35.5 | 8.72 | 35
8 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/B WATER SUPPLY SCHEME | SM/14091 | Augmentation | SOIL INVESTIGATION FOR PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN KHATRA SUB DIVITION OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 643/BQA | 24/03/2023 | 23/04/2023 | P. K. TEWARY DRILLING CO | 8.41 | 0.84 | 10 | 99
9 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/B WATER SUPPLY SCHEME | SM/14091 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 2.26 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/B WATER SUPPLY SCHEME | SM/14091 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000206/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 14.2 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/B WATER SUPPLY SCHEME | SM/14091 | Augmentation | Work Order Installation of scheme information board for 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- IV/B Water supply scheme (SM/14091), 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- V/A Water supply scheme (SM/15009), 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- V/B Water supply scheme (SM/16935), 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- VI Water supply scheme (SM/16260),1 no. site of Sub surface water based Pirrabakra pipe water supply scheme (SM/18042) and 1 no. site of Proposed sub surface water based Khayerbani pipe water supply scheme (SM/18040) within Khatra Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001910/2024-2025 | 154\KSD | 07/03/2025 | 17/03/2025 | TAPAN KUMAR MANDAL | 0.9 | 0 | 0 | 90
Total | [13 empty] | 480.06 | 39.77 | 8.28