## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Kotulpur | Bankura Division | Dhula Danga Piped Water Supply Scheme | SM/14176 | New | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 73.19 | 0 | 0 | 0
2 | BANKURA | Kotulpur | Bankura Mechanical | Dhula Danga Piped Water Supply Scheme | SM/14176 | New | New service connection of P/H-II Dhuladanga W/S scheme |  |  | BILL/00599/2024-2025 | BP-2024-25-169 | 06/08/2024 | 06/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.62 | 0 | 0 | 0
3 | BANKURA | Kotulpur | Bankura Division | Dhula Danga Piped Water Supply Scheme | SM/14176 | New | Instalation of scheme information board for 2 nos. sites of Gopalpur Piped Water Supply Scheme (SM/16698) , 2 nos. sites of Dhula Danga Piped Water Supply Scheme (SM/14176) & 2 nos. sites of Adwaitabati Piped Water Supply Scheme (SM/16942) within Kotulpur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001876/2024-2025 | 554/VSD | 27/09/2024 | 12/10/2024 | SAFIQUE AHAMMAD KHAN | 0.9 | 0 | 0 | 100
4 | BANKURA | Kotulpur | Bankura Mechanical | Dhula Danga Piped Water Supply Scheme | SM/14176 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Dhuladanga Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000144/2025-2026 | 439/BMD | 10/06/2025 | 08/09/2025 | M/S SAJAHAN CHOWDHURY | 11.85 | 0 | 0 | 0
Total | [13 empty] | 90.56 | 0 | 0