## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Kotulpur | Bankura Division | Narayanpur Piped Water Supply Scheme | SM/14178 | New | Material Requisition To Resource Division |  |  | RTOR000092/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 48.16 | 0 | 0 | 0
2 | BANKURA | Kotulpur | Bankura Division | Narayanpur Piped Water Supply Scheme | SM/14178 | New | Material Requisition To Resource Division |  |  | RTOR000019/2024-2025 | 2994/BQA | 28/11/2024 | 28/11/2024 | Resource Division | 12.2 | 0 | 0 | 0
3 | BANKURA | Kotulpur | Bankura Mechanical | Narayanpur Piped Water Supply Scheme | SM/14178 | New | Narayanpur |  |  | BILL/01505/2023-2024 | BP-2023-24-101 | 15/02/2024 | 15/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.1 | 0 | 0 | 0
4 | BANKURA | Kotulpur | Bankura Division | Narayanpur Piped Water Supply Scheme | SM/14178 | New | Instalation of scheme information board for 2 nos. sites of Pratappur Piped Water Supply Scheme (SM/15019), 2 nos. sites of Narayanpur Piped Water Supply Scheme (SM/14178) & 2 nos. sites of Lankajol Piped Water Supply Scheme (SM/15022) within Kotulpur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001879/2024-2025 | 557/VSD | 27/09/2024 | 12/10/2024 | SAFIQUE AHAMMAD KHAN | 0.9 | 0 | 0 | 100
5 | BANKURA | Kotulpur | Bankura Mechanical | Narayanpur Piped Water Supply Scheme | SM/14178 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR at Narayanpur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 445/BMD | 10/06/2025 | 08/09/2025 | GOPAL CHANDRA CHOWDHURY | 11.87 | 0 | 0 | 0
6 | BANKURA | Kotulpur | Bankura Division | Narayanpur Piped Water Supply Scheme | SM/14178 | New | Gopinathpur to Aswinkota ( WB-03-432) of Scheme Name Narayanpur PWSS (SM/14178) |  |  | BILL/02021/2024-2025 |  | 25/03/2025 | 25/03/2025 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 13.86 | 0 | 0 | 0
7 | BANKURA | Kotulpur | Bankura Division | Narayanpur Piped Water Supply Scheme | SM/14178 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 31/12/2024 | MACKINTOSH BURN LIMITED | 13769.53 | 152.61 | 1.11 | 55
Total | [13 empty] | 13865.62 | 152.61 | 1.1