## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Sonamukhi | Bankura Division | Chakai Piped Water Supply Scheme | SM/14245 | New | Material Requisition To Resource Division |  |  | RTOR000030/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 140.84 | 0 | 0 | 0
2 | BANKURA | Sonamukhi | Bankura Mechanical | Chakai Piped Water Supply Scheme | SM/14245 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II of Chakai Piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000106/2023-2024 | 768/BMD | 24/04/2023 | 21/10/2023 | GOENKA ENTERPRISE | 47 | 0 | 0 | 60
3 | BANKURA | Sonamukhi | Bankura Division | Chakai Piped Water Supply Scheme | SM/14245 | New | Material Requisition To Resource Division |  |  | RTOR000016/2024-2025 | 2944/BQA | 21/11/2024 | 21/11/2024 | Resource Division | 4.83 | 0 | 0 | 0
4 | BANKURA | Sonamukhi | Bankura Division | Chakai Piped Water Supply Scheme | SM/14245 | New | Road Name: L049-Paschimdubrajpur to Sitaljore Package No: WB-03-666 Name of the Block: Sonamukhi Name of the District: Bankura Length of Road: 1.180 Km Damaged Length: 300.000 m (Due to both side cutting) SM/14245 CHAKAI PWSS |  |  | BILL/01250/2024-2025 | BP-436/2024-25 | 28/11/2024 | 28/11/2024 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 0.58 | 0 | 0 | 0
5 | BANKURA | Sonamukhi | Bankura Mechanical | Chakai Piped Water Supply Scheme | SM/14245 | New | New Service Connection for CHAKAI (JL NO-23, PLOT-177) Water supply scheme under Bankura Mechanical Division PHE DTE |  |  | BILL/00018/2024-2025 | BP-2024-25-26 | 10/05/2024 | 10/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.28 | 0 | 0 | 0
6 | BANKURA | Sonamukhi | Bankura Mechanical | Chakai Piped Water Supply Scheme | SM/14245 | New | Chakai Piped Water Supply Scheme |  |  | BILL/01665/2023-2024 | BP-2023-24-192 | 27/03/2024 | 27/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.36 | 0 | 0 | 0
7 | BANKURA | Sonamukhi | Bankura Division | Chakai Piped Water Supply Scheme | SM/14245 | New | Road Name: Prayagpur to 21L20 Package No: WB-03-774 Name of the Block: Sonamukhi Name of the District: Bankura Length of Road: 1.650 Km Damaged Length: 3080.000 m (Due to some portion Both Side Cutting) SM/14245 CHAKAI PWSS |  |  | BILL/01249/2024-2025 | BP-437/2024-25 | 28/11/2024 | 28/11/2024 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 4.85 | 0 | 0 | 0
8 | BANKURA | Sonamukhi | Bankura Division | Chakai Piped Water Supply Scheme | SM/14245 | New | Repair and Maintenance work of the Road from Palashdanga to T12 under Sonamukhi Block in the District to Bankura ,Vide Package No-WB-03-50, Road Length- 16.80 Km. Scheme code for i) chakai PWSS (ch-3000m to ch- 7100m)- SM/14245 ii) Birsinghapur pwss (ch- 9400m to 12100m)- SM/17223 iii) Dhulai PWSS (Ch-13100m to 16800m)- SM/18753 |  |  | BILL/01251/2024-2025 | BP-439/2024-25 | 28/11/2024 | 28/11/2024 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 30.91 | 0 | 0 | 0
9 | BANKURA | Sonamukhi | Bankura Division | Chakai Piped Water Supply Scheme | SM/14245 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR CHAKAI & KUBIRBANDH PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000484/2023-2024 | 2336/BQA | 14/08/2023 | 09/05/2026 | PRINCE INDUTRIES (INDIA) | 1048.51 | 0 | 0 | 73
10 | BANKURA | Sonamukhi | Bankura Division | Chakai Piped Water Supply Scheme | SM/14245 | New | Balance Ancillary Work for ¿Kubirbandh¿ and ¿Chakai¿ Piped Water Supply Scheme, Sonamukhi Block, Bishnupur Sub Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000422/2025-2026 | 1989/BQA | 16/09/2025 | 15/03/2026 | PRINCE INDUSTRIES (INDIA) | 130.51 | 0 | 0 | 15
Total | [13 empty] | 1417.68 | 0 | 0