## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Kotulpur | Bankura Division | Deshra Piped Water Supply Scheme | SM/14246 | New | Material Requisition To Resource Division |  |  | RTOR000032/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 95.48 | 0 | 0 | 0
2 | BANKURA | Kotulpur | Bankura Division | Deshra Piped Water Supply Scheme | SM/14246 | New | Instalation of scheme information board for 3 nos. sites of Deshra Piped Water Supply Scheme (SM/14246) & 3 nos. sites of Baragaria Piped Water Supply Scheme (SM/18789) within Kotulpur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001878/2024-2025 | 556/VSD | 27/09/2024 | 12/10/2024 | SAFIQUE AHAMMAD KHAN | 0.9 | 0 | 0 | 100
3 | BANKURA | Kotulpur | Bankura Mechanical | Deshra Piped Water Supply Scheme | SM/14246 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Deshra Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000143/2025-2026 | 438/BMD | 10/06/2025 | 08/09/2025 | KINGKINI TRADERS | 12.94 | 0 | 0 | 0
Total | [13 empty] | 109.32 | 0 | 0