## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Kotulpur | Bankura Division | Nandagram Piped Water Supply Scheme | SM/14248 | New | Material Requisition To Resource Division |  |  | RTOR000091/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 105.33 | 0 | 0 | 0
2 | BANKURA | Kotulpur | Bankura Division | Nandagram Piped Water Supply Scheme | SM/14248 | New | Material Requisition To Resource Division |  |  | RTOR000023/2024-2025 | 2994/BQA | 28/11/2024 | 28/11/2024 | Resource Division | 19.29 | 0 | 0 | 0
3 | BANKURA | Kotulpur | Bankura Mechanical | Nandagram Piped Water Supply Scheme | SM/14248 | New | Nandagram Piped Water Supply Scheme |  |  | BILL/01502/2023-2024 | BP-2023-24-100 | 15/02/2024 | 15/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 18.36 | 0 | 0 | 0
4 | BANKURA | Kotulpur | Bankura Division | Nandagram Piped Water Supply Scheme | SM/14248 | New | Construction of FHTC Platform, Sinking of Tubewell and Construction of Boundary Wall & Pump House for Augmentation of Joyrambati Piped Water Supply Scheme & Nandagram Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001936/2024-2025 | 657/BQA | 11/03/2025 | 09/06/2025 | S B ASSOCIATES | 63.67 | 0 | 0 | 0
5 | BANKURA | Kotulpur | Bankura Division | Nandagram Piped Water Supply Scheme | SM/14248 | New | Instalation of scheme information board for 3 nos. sites of Nandagram Piped Water Supply Scheme (SM/14248) & 2 nos. sites of Khiri Piped Water Supply Scheme (SM/18436) within Kotulpur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001881/2024-2025 | 559/VSD | 27/09/2024 | 12/10/2024 | SAFIQUE AHAMMAD KHAN | 0.75 | 0 | 0 | 100
6 | BANKURA | Kotulpur | Bankura Mechanical | Nandagram Piped Water Supply Scheme | SM/14248 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Nandagram Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000149/2025-2026 | 444/BMD | 10/06/2025 | 08/09/2025 | AMITAVA CHAKRABORTY | 12.97 | 0 | 0 | 0
7 | BANKURA | Kotulpur | Bankura Division | Nandagram Piped Water Supply Scheme | SM/14248 | New | Supply, delivery, installation of PVC flex containing information of schemes of JJM within Joypur & Sonamukhi Blocks under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001777/2024-2025 | 464/VSD | 16/08/2024 | 26/08/2024 | PARTHA ROY | 2.16 | 0 | 0 | 100
Total | [13 empty] | 222.54 | 0 | 0