## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mouzas under Lurka (Zone - VB) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) at Block - Raipur, Dist - Bankura under Jal Jeevan Mission Programme. | SM/14491 | Retrofitting | Work Order for Water supply arrangement at different Anganwadi Centre by laying pipeline and installation of stand post under Lurka Zone-B of Raipur Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Under Jal Swapna & Jal Jeevan Mission Programme) (Sl. No. 03) | Assistant Engineer |  | ORD/001084/2021-2022 | 22\KSD | 10/02/2022 | 12/03/2022 | SUNIL KUMAR MANDAL | 3.69 | 0 | 0 | 95
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mouzas under Lurka (Zone - VB) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) at Block - Raipur, Dist - Bankura under Jal Jeevan Mission Programme. | SM/14491 | Retrofitting | Work Order for Water supply arrangement at different School by laying pipeline and installation of stand post under Lurka Zone-B of Raipur Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Under Jal Swapna & Jal Jeevan Mission Programme) | Assistant Engineer |  | ORD/001086/2021-2022 | 23\KSD | 10/02/2022 | 12/03/2022 | ANATH DANDAPAT | 2.78 | 0 | 0 | 95
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mouzas under Lurka (Zone - VB) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) at Block - Raipur, Dist - Bankura under Jal Jeevan Mission Programme. | SM/14491 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 2412/BQA | 18/08/2023 | 18/08/2023 | Resource Division | 23.21 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mouzas under Lurka (Zone - VB) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) at Block - Raipur, Dist - Bankura under Jal Jeevan Mission Programme. | SM/14491 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jamda (307), Shubnabandi (308), Krishna Nagar (309), Narayanpur (310), Barkala (320), Dharampur (321), Sirsa (322), Maulasol (323), Lurka (324), Gochda (325) & Lagda (326) mouzas under Lurka (Zone-VB) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000111/2023-2024 | 1193/BQA | 22/05/2023 | 20/08/2023 | SIB SANKAR CHOWDHURY | 280.1 | 0 | 0 | 65
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mouzas under Lurka (Zone - VB) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) at Block - Raipur, Dist - Bankura under Jal Jeevan Mission Programme. | SM/14491 | Retrofitting | Laying HDPE pipeline with allied works for construction and commissioning of FHTC (Functional House Hold Tap Connection) under Lurka (Zone-VB) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001129/2023-2024 | 248/BQA | 25/01/2024 | 01/04/2025 | TAPAN KUMAR MANDAL | 34.52 | 0 | 0 | 50
Total | [13 empty] | 344.31 | 0 | 0