## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Sonamukhi | Bankura Division | Ranpur Piped Water Supply Scheme | SM/14519 | New | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 101.28 | 0 | 0 | 0
2 | BANKURA | Sonamukhi | Bankura Division | Ranpur Piped Water Supply Scheme | SM/14519 | New | Material Requisition To Resource Division |  |  | RTOR000018/2024-2025 | 2994/BQA | 28/11/2024 | 28/11/2024 | Resource Division | 23.34 | 0 | 0 | 0
3 | BANKURA | Sonamukhi | Bankura Mechanical | Ranpur Piped Water Supply Scheme | SM/14519 | New | New Service Connection for RANPUR( JL NO-141,PLOT NO-676LR)Water supply scheme under Bankura Mechanical Division PHE DTE |  |  | BILL/00019/2024-2025 | BP-2024-25-25 | 10/06/2024 | 10/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.2 | 0 | 0 | 0
4 | BANKURA | Sonamukhi | Bankura Mechanical | Ranpur Piped Water Supply Scheme | SM/14519 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Ranpur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000155/2025-2026 | 450/BMD | 10/06/2025 | 08/09/2025 | M/S NABIN GOPAL SENGUPTA | 13.1 | 0 | 0 | 0
Total | [13 empty] | 141.92 | 0 | 0