## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Jaypur | Bankura Division | Makarandapur Piped Water Supply Scheme | SM/14520 | New | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 23/03/2023 | MABCO CONSULTANT | 15.12 | 0 | 0 | 30
2 | BANKURA | Jaypur | Bankura Division | Makarandapur Piped Water Supply Scheme | SM/14520 | New | Material Requisition To Resource Division |  |  | RTOR000064/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 188.77 | 0 | 0 | 0
3 | BANKURA | Jaypur | Bankura Mechanical | Makarandapur Piped Water Supply Scheme | SM/14520 | New | New service connection at Makarandapur Piped Water Supply Scheme t/w-I ,Makarandapur(Magura) of joypur block under BMD PHE Dte. |  |  | BILL/00132/2024-2025 | BP-2024-25-24 | 10/05/2024 | 10/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.8 | 0 | 0 | 0
4 | BANKURA | Jaypur | Bankura Mechanical | Makarandapur Piped Water Supply Scheme | SM/14520 | New | New service connection at Makarandapur Piped Water Supply Scheme t/w-II ,Makarandapur(Adhakata) of joypur block under BMD PHE Dte. |  |  | BILL/00131/2024-2025 | BP-2024-25-23 | 10/05/2024 | 10/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.34 | 0 | 0 | 0
5 | BANKURA | Jaypur | Bankura Mechanical | Makarandapur Piped Water Supply Scheme | SM/14520 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Markandapur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000186/2025-2026 | 458/BMD | 10/06/2025 | 08/09/2025 | M/S SOMA ENTERPRISES | 11.86 | 0 | 0 | 0
Total | [13 empty] | 222.9 | 0 | 0