## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Jaypur | Bankura Division | Makarandapur Piped Water Supply Scheme | SM/14520 | New | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 23/03/2023 | MABCO CONSULTANT | 15.12 | 1.08 | 7.14 | 30
2 | BANKURA | Jaypur | Bankura Division | Makarandapur Piped Water Supply Scheme | SM/14520 | New | Material Requisition To Resource Division |  |  | RTOR000064/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 188.77 | 0 | 0 | 0
3 | BANKURA | Jaypur | Bankura Mechanical | Makarandapur Piped Water Supply Scheme | SM/14520 | New | New service connection at Makarandapur Piped Water Supply Scheme t/w-I ,Makarandapur(Magura) of joypur block under BMD PHE Dte. |  |  | BILL/00132/2024-2025 | BP-2024-25-24 | 10/05/2024 | 10/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.8 | 0 | 0 | 0
4 | BANKURA | Jaypur | Bankura Mechanical | Makarandapur Piped Water Supply Scheme | SM/14520 | New | New service connection at Makarandapur Piped Water Supply Scheme t/w-II ,Makarandapur(Adhakata) of joypur block under BMD PHE Dte. |  |  | BILL/00131/2024-2025 | BP-2024-25-23 | 10/05/2024 | 10/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.34 | 0 | 0 | 0
5 | BANKURA | Jaypur | Bankura Mechanical | Makarandapur Piped Water Supply Scheme | SM/14520 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Markandapur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000186/2025-2026 | 458/BMD | 10/06/2025 | 08/09/2025 | M/S SOMA ENTERPRISES | 11.86 | 0 | 0 | 0
6 | BANKURA | Jaypur | Bankura Division | Makarandapur Piped Water Supply Scheme | SM/14520 | New | Instalation of scheme information board for 2 nos. sites of Makarandapur Piped Water Supply Scheme (SM/14520) , 2 nos. sites of Hirapur Piped Water Supply Scheme (SM/12418) & 2 nos. sites of Nabasan Piped Water Supply Scheme (SM/13874) within Joypur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001834/2024-2025 | 548/VSD | 27/09/2024 | 12/10/2024 | SUBHANKAR BIT | 0.9 | 0 | 0 | 0
7 | BANKURA | Jaypur | Bankura Division | Makarandapur Piped Water Supply Scheme | SM/14520 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GHAGARA, KATABAN, BASANTAPUR, HETIA, ROUTHKHANDA, HIRAPUR, NABASAN, BANNA, PANKHAI, MADHABBATI & MAKARANDAPUR PIPED WATER SUPPLY SCHEME OF JOYPUR BLOCK AND KARAKBERYA, KHIRI, LAUGRAM & PATRABANDH PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK , DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 2025/BQA | 24/07/2023 | 31/12/2024 | MACKINTOSH BURN LIMITED | 11091.12 | 298.09 | 2.69 | 6
Total | [13 empty] | 11314.92 | 299.17 | 2.64