## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Sonamukhi | Bankura Division | Rautara Piped Water Supply Scheme | SM/14521 | New | Material Requisition To Resource Division |  |  | RTOR000074/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 156.61 | 0 | 0 | 0
2 | BANKURA | Sonamukhi | Bankura Mechanical | Rautara Piped Water Supply Scheme | SM/14521 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR at Routara Piped Water Supply Scheme under BMD PHE Dte Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000069/2025-2026 | 260/BMD | 14/05/2025 | 12/08/2025 | SUMIT KUMAR CHAKRABORTY | 11.66 | 0 | 0 | 0
3 | BANKURA | Sonamukhi | Bankura Division | Rautara Piped Water Supply Scheme | SM/14521 | New | Instalation of scheme information board for 2 nos. sites of Rautara Piped Water Supply Scheme (SM/14521) & 3 nos. sites of Brindabanpur Piped Water Supply Scheme (SM/18437) within Sonamukhi Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001897/2024-2025 | 575/VSD | 27/09/2024 | 12/10/2024 | PARTHA ROY | 0.75 | 0 | 0 | 0
4 | BANKURA | Sonamukhi | Bankura Mechanical | Rautara Piped Water Supply Scheme | SM/14521 | New | Additional quotation for Rautora. |  |  | BILL/00367/2025-2026 | 107/W-612 | 01/08/2025 | 01/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.16 | 0 | 0 | 0
5 | BANKURA | Sonamukhi | Bankura Division | Rautara Piped Water Supply Scheme | SM/14521 | New | The maintenance and repair estimate is prepared in respect of the road namely T05-Melhra to 21L2 having Package No -WB-03-658 under Sonamukhi block, in the District of Bankura under PMGSY ,WBSRDA , Bishnupur Division. Road Name : METHRA to 21 LZ (WB-03-658) From Telrui Piped Water Supply Scheme (SM/13711 ) |  |  | BILL/00471/2025-2026 |  | 20/06/2025 | 20/06/2025 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 3.46 | 0 | 0 | 0
6 | BANKURA | Sonamukhi | Bankura Mechanical | Rautara Piped Water Supply Scheme | SM/14521 | New | New three phase service Connection for RautaraTW2 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/14521) |  |  | BILL/01249/2024-2025 | BP-2024-25-323 | 16/12/2024 | 16/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 13.47 | 0 | 0 | 0
7 | BANKURA | Sonamukhi | Bankura Mechanical | Rautara Piped Water Supply Scheme | SM/14521 | New | New three phase service Connection for Rautara TW1 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/14521) |  |  | BILL/01250/2024-2025 | BP-2024-25-324 | 16/12/2024 | 16/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.65 | 0 | 0 | 0
8 | BANKURA | Sonamukhi | Bankura Division | Rautara Piped Water Supply Scheme | SM/14521 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PATSOL, RAUTARA, BRINDABANPUR, TELRUI, RANPUR, NANDAMOHANPUR & NARUALA PIPED WATER SUPPLY SCHEME OF SONAMUKHI BLOCK , DHULA DANGA, LEGO, NARAYANPUR, PRATAPPUR, NANDAGRAM, LANKAJOL & DESHRA PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK AND BINOD NAGAR, JAMKURI, GOALA, KUSHADWIP, MUKUNDAPUR & NANDUR PIPED WATER SUPPLY SCHEME OF PATRASAYER BLOCK, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 2024/BQA | 24/07/2023 | 31/12/2024 | MACKINTOSH BURN LIMITED | 13769.53 | 26.18 | 0.19 | 55
Total | [13 empty] | 13963.31 | 26.18 | 0.19