## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Jaypur | Bankura Division | Danga Makarandapur Piped Water Supply Scheme | SM/14523 | New | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 23/03/2023 | MABCO CONSULTANT | 15.12 | 1.08 | 7.14 | 30
2 | BANKURA | Jaypur | Bankura Division | Danga Makarandapur Piped Water Supply Scheme | SM/14523 | New | Material Requisition To Resource Division |  |  | RTOR000084/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 119.65 | 0 | 0 | 0
3 | BANKURA | Jaypur | Bankura Division | Danga Makarandapur Piped Water Supply Scheme | SM/14523 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR DANGA MAKARANDAPUR PIPED WATER SUPPLY SCHEME, BLOCK- JOYPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000381/2023-2024 | 2042/BOQ | 24/07/2023 | 01/04/2026 | M/S TARUN KUMAR PATRA | 808.13 | 475.53 | 58.84 | 85
4 | BANKURA | Jaypur | Bankura Mechanical | Danga Makarandapur Piped Water Supply Scheme | SM/14523 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Danga Makarandapur piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Joypur , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000383/2023-2024 | 1706/BMD | 28/07/2023 | 26/09/2023 | P.K. ENGINEERING | 59.05 | 27.6 | 46.74 | 20
5 | BANKURA | Jaypur | Bankura Division | Danga Makarandapur Piped Water Supply Scheme | SM/14523 | New | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 1637/BQA | 28/06/2024 | 28/06/2024 | Resource Division | 15.8 | 0 | 0 | 0
6 | BANKURA | Jaypur | Bankura Mechanical | Danga Makarandapur Piped Water Supply Scheme | SM/14523 | New | Dangamakrandapur T/W-II |  |  | BILL/00852/2023-2024 | BP-2023-24-45 | 18/12/2023 | 18/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.48 | 0 | 0 | 0
7 | BANKURA | Jaypur | Bankura Mechanical | Danga Makarandapur Piped Water Supply Scheme | SM/14523 | New | Dangamakrandapur T/W-I |  |  | BILL/00851/2023-2024 | BP-2023-24-44 | 18/12/2023 | 18/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.95 | 0 | 0 | 0
8 | BANKURA | Jaypur | Bankura Division | Danga Makarandapur Piped Water Supply Scheme | SM/14523 | New | Additional work of Road Crossing for Jack Pussing of Danga Makarandapur Water Supply Scheme under Joypur Block under Bishnupur Sub vision of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000873/2023-2024 | 3004/BQA | 03/11/2023 | 01/04/2026 | M/S TARUN KUMAR PATRA | 34.85 | 0 | 0 | 95
Total | [13 empty] | 1059.03 | 504.22 | 47.61