## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Jaypur | Bankura Division | Rautkhanda Piped Water Supply Scheme | SM/14524 | New | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 23/03/2023 | MABCO CONSULTANT | 15.12 | 1.08 | 7.14 | 30
2 | BANKURA | Jaypur | Bankura Division | Rautkhanda Piped Water Supply Scheme | SM/14524 | New | Material Requisition To Resource Division |  |  | RTOR000077/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 80.11 | 0 | 0 | 0
3 | BANKURA | Jaypur | Bankura Division | Rautkhanda Piped Water Supply Scheme | SM/14524 | New | Material Requisition To Resource Division |  |  | RTOR000299/2023-2024 | 884/BQA | 12/03/2024 | 12/03/2024 | Resource Division | 21.32 | 0 | 0 | 0
4 | BANKURA | Jaypur | Bankura Mechanical | Rautkhanda Piped Water Supply Scheme | SM/14524 | New | Rautkhanda Piped Water Supply Scheme |  |  | BILL/01511/2023-2024 | BP-2023-24-98 | 15/02/2024 | 15/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.6 | 0 | 0 | 0
5 | BANKURA | Jaypur | Bankura Mechanical | Rautkhanda Piped Water Supply Scheme | SM/14524 | New | New service connection at Basantapur Piped Water Supply Scheme t/w-II ,Basantapur, Routhkhanda of joypur block under BMD PHE Dte. |  |  | BILL/00135/2024-2025 | BP-2024-25-21 | 10/06/2024 | 10/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.34 | 0 | 0 | 0
6 | BANKURA | Jaypur | Bankura Mechanical | Rautkhanda Piped Water Supply Scheme | SM/14524 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Routhkhanda Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000182/2025-2026 | 454/BMD | 10/06/2025 | 08/09/2025 | DEY ENTERPRISE | 13.05 | 0 | 0 | 0
7 | BANKURA | Jaypur | Bankura Division | Rautkhanda Piped Water Supply Scheme | SM/14524 | New | Instalation of scheme information board for 2 nos. sites of Ghagara Piped Water Supply Scheme (SM/12426) & 3 nos. sites of Rautkhanda Piped Water Supply Scheme (SM/14524) within Joypur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001829/2024-2025 | 546/VSD | 27/09/2024 | 12/10/2024 | SUBHANKAR BIT | 0.75 | 0 | 0 | 0
8 | BANKURA | Jaypur | Bankura Mechanical | Rautkhanda Piped Water Supply Scheme | SM/14524 | New | New service connection at Routhkhanda Piped Water Supply Scheme t/w-II ,Routhkhanda gp of joypur block under BMD PHE Dte. |  |  | BILL/01243/2024-2025 | BP-2024-25-315 | 10/12/2024 | 10/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.59 | 0 | 0 | 0
9 | BANKURA | Jaypur | Bankura Mechanical | Rautkhanda Piped Water Supply Scheme | SM/14524 | New | New service connection at Routhkhanda Piped Water Supply Scheme t/w-III ,Routhkhanda gp of joypur block under BMD PHE Dte. |  |  | BILL/01242/2024-2025 | BP-2024-25-314 | 10/12/2024 | 10/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.14 | 0 | 0 | 0
10 | BANKURA | Jaypur | Bankura Division | Rautkhanda Piped Water Supply Scheme | SM/14524 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GHAGARA, KATABAN, BASANTAPUR, HETIA, ROUTHKHANDA, HIRAPUR, NABASAN, BANNA, PANKHAI, MADHABBATI & MAKARANDAPUR PIPED WATER SUPPLY SCHEME OF JOYPUR BLOCK AND KARAKBERYA, KHIRI, LAUGRAM & PATRABANDH PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK , DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 2025/BQA | 24/07/2023 | 31/12/2024 | MACKINTOSH BURN LIMITED | 11091.12 | 368.35 | 3.32 | 6
Total | [13 empty] | 11236.15 | 369.43 | 3.29