## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Jaypur | Bankura Division | Banna Piped Water Supply Scheme | SM/14525 | New | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 23/03/2023 | MABCO CONSULTANT | 15.12 | 1.08 | 7.14 | 30
2 | BANKURA | Jaypur | Bankura Division | Banna Piped Water Supply Scheme | SM/14525 | New | Material Requisition To Resource Division |  |  | RTOR000029/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 174.48 | 0 | 0 | 0
3 | BANKURA | Jaypur | Bankura Mechanical | Banna Piped Water Supply Scheme | SM/14525 | New | Banna Piped Water Supply Scheme |  |  | BILL/01496/2023-2024 | BP-2023-24-97 | 15/02/2024 | 15/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.96 | 0 | 0 | 0
4 | BANKURA | Jaypur | Bankura Mechanical | Banna Piped Water Supply Scheme | SM/14525 | New | New service connection at Banna Piped Water Supply Scheme t/w-III ,Banna (Gelia Ruidas Para) of joypur block under BMD PHE Dte. |  |  | BILL/00139/2024-2025 | BP-2024-25-20 | 10/05/2024 | 10/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.57 | 0 | 0 | 0
5 | BANKURA | Jaypur | Bankura Mechanical | Banna Piped Water Supply Scheme | SM/14525 | New | New service connection at Banna Piped Water Supply Scheme t/w-II ,Banna (Lokepur) of joypur block under BMD PHE Dte. |  |  | BILL/00137/2024-2025 | BP-2024-25-19 | 10/05/2024 | 10/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.64 | 0 | 0 | 0
6 | BANKURA | Jaypur | Bankura Mechanical | Banna Piped Water Supply Scheme | SM/14525 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Banna Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000181/2025-2026 | 453/BMD | 10/06/2025 | 08/09/2025 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 12.93 | 0 | 0 | 0
7 | BANKURA | Jaypur | Bankura Division | Banna Piped Water Supply Scheme | SM/14525 | New | Instalation of scheme information board for 2 nos. sites of Kataban Piped Water Supply Scheme (SM/14526) & 3 nos. sites of Banna Piped Water Supply Scheme (SM/14525) within Joypur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001837/2024-2025 | 550/VSD | 27/09/2024 | 12/10/2024 | SUBHANKAR BIT | 0.75 | 0 | 0 | 0
Total | [13 empty] | 221.45 | 1.08 | 0.49