## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Jaypur | Bankura Division | Kataban Piped Water Supply Scheme | SM/14526 | New | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 23/03/2023 | MABCO CONSULTANT | 15.12 | 1.08 | 7.14 | 30
2 | BANKURA | Jaypur | Bankura Division | Kataban Piped Water Supply Scheme | SM/14526 | New | Material Requisition To Resource Division |  |  | RTOR000049/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 47.47 | 0 | 0 | 0
3 | BANKURA | Jaypur | Bankura Division | Kataban Piped Water Supply Scheme | SM/14526 | New | Material Requisition To Resource Division |  |  | RTOR000300/2023-2024 | 884/BQA | 12/03/2024 | 12/03/2024 | Resource Division | 13.76 | 0 | 0 | 0
4 | BANKURA | Jaypur | Bankura Mechanical | Kataban Piped Water Supply Scheme | SM/14526 | New | Kataban Piped Water Supply Scheme |  |  | BILL/01605/2023-2024 | BP-2023-24-141 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.35 | 0 | 0 | 0
5 | BANKURA | Jaypur | Bankura Division | Kataban Piped Water Supply Scheme | SM/14526 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL & ELECTRO MECHANICAL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GHAGARA, KATABAN, BASANTAPUR, HETIA, ROUTHKHANDA, HIRAPUR, NABASAN, BANNA, PANKHAI, MADHABBATI & MAKARANDAPUR PIPED WATER SUPPLY SCHEME OF JOYPUR BLOCK AND KARAKBERYA, KHIRI, LAUGRAM & PATRABANDH PIPED WATER SUPPLY SCHEME OF KOTULPUR BLOCK , DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 2025/BQA | 24/07/2023 | 31/12/2024 | MACKINTOSH BURN LIMITED | 11091.12 | 321.97 | 2.9 | 6
6 | BANKURA | Jaypur | Bankura Mechanical | Kataban Piped Water Supply Scheme | SM/14526 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for proposed ground water based Katabani piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Onda Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000528/2023-2024 | 1892/BMD | 17/08/2023 | 06/08/2025 | MENAKA ENTERPRISE | 36.9 | 21.69 | 58.78 | 90
7 | BANKURA | Jaypur | Bankura Mechanical | Kataban Piped Water Supply Scheme | SM/14526 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Kantaban Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000183/2025-2026 | 455/BMD | 10/06/2025 | 08/09/2025 | JAL PRAVAHIKA PVT LTD | 11.85 | 0 | 0 | 0
Total | [13 empty] | 11220.57 | 344.73 | 3.07