## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Jaypur | Bankura Division | Jadabnagar Piped Water Supply Scheme | SM/14527 | New | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 1120/BQA | 12/05/2023 |  | Resource Division | 74.23 | 0 | 0 | 0
2 | BANKURA | Jaypur | Bankura Division | Jadabnagar Piped Water Supply Scheme | SM/14527 | New | Material Requisition To Resource Division |  |  | RTOR000058/2023-2024 | 2524/BQA | 08/09/2023 |  | Resource Division | 18.03 | 0 | 0 | 0
3 | BANKURA | Jaypur | Bankura Division | Jadabnagar Piped Water Supply Scheme | SM/14527 | New | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 23/03/2023 | MABCO CONSULTANT | 15.12 | 0 | 0 | 30
4 | BANKURA | Jaypur | Bankura Mechanical | Jadabnagar Piped Water Supply Scheme | SM/14527 | New | Jadabnagar T/W-I |  |  | BILL/00848/2023-2024 | BP-2023-24-41 | 18/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.08 | 0 | 0 | 0
5 | BANKURA | Jaypur | Bankura Mechanical | Jadabnagar Piped Water Supply Scheme | SM/14527 | New | Jadabnagar T/W-II |  |  | BILL/00849/2023-2024 | BP-2023-24-42 | 18/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.87 | 0 | 0 | 0
6 | BANKURA | Jaypur | Bankura Mechanical | Jadabnagar Piped Water Supply Scheme | SM/14527 | New | Jadabnagar T/W-II |  |  | BILL/00849/2023-2024 | BP-2023-24-42 | 18/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.87 | 0 | 0 | 0
7 | BANKURA | Jaypur | Bankura Mechanical | Jadabnagar Piped Water Supply Scheme | SM/14527 | New | Jadabnagar T/W-III |  |  | BILL/00850/2023-2024 | BP-2023-24-43 | 18/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.56 | 0 | 0 | 0
8 | BANKURA | Jaypur | Bankura Division | Jadabnagar Piped Water Supply Scheme | SM/14527 | New | Material Requisition To Resource Division |  |  | RTOR000154/2023-2024 | 111/BQA | 10/01/2024 |  | Resource Division | 18.03 | 0 | 0 | 0
9 | BANKURA | Jaypur | Bankura Division | Jadabnagar Piped Water Supply Scheme | SM/14527 | New | Jack Pussing, Land development & Rock cutting for foundation of 500 M3 capacity RCC OHR with 20 Mtr. staging height of Jadabnagar Water Supply Scheme & 450 M3 capacity RCC OHR with 20 Mtr. staging height of Harinasuli Water Supply Scheme under Bishnupur Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000869/2023-2024 | 3001/BQA | 03/11/2023 | 18/12/2023 | GOPAL CHANDRA CHOWDHURY | 74.67 | 0 | 0 | 95
10 | BANKURA | Jaypur | Bankura Mechanical | Jadabnagar Piped Water Supply Scheme | SM/14527 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Jadabnagar piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Joypur , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000165/2023-2024 | 877/BMD | 04/05/2023 | 31/10/2023 | EASTERN INDIA SALES & SERVICE | 59.05 | 14.74 | 24.96 | 55
11 | BANKURA | Jaypur | Bankura Division | Jadabnagar Piped Water Supply Scheme | SM/14527 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR HARINASHULI & JADABNAGAR PIPED WATER SUPPLY SCHEME, BLOCK- JOYPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000301/2023-2024 | 1918/BQA | 13/07/2023 | 08/04/2024 | GOPAL CHANDRA CHOWDHURY | 1591.82 | 0 | 0 | 25
Total | [13 empty] | 1868.33 | 14.74 | 0.79