## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/A WATER SUPPLY SCHEME | SM/14650 | Augmentation | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone 7A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000243/2023-2024 | 1128/BMD | 24/05/2023 | 23/06/2023 | CHAKRABORTY MINING & ENGINEERING. | 2.39 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/A WATER SUPPLY SCHEME | SM/14650 | Augmentation | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Ranibandh, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-7A) (Sl. No. 12) |  | Junior Engineer | ORD/000632/2022-2023 | 190/KSD | 24/05/2022 | 08/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.89 | 2.41 | 83.43 | 0
3 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/A WATER SUPPLY SCHEME | SM/14650 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000210/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 1.13 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/A WATER SUPPLY SCHEME | SM/14650 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone- VII/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001305/2023-2024 | 908/BQA | 14/03/2024 | 12/06/2024 | GON ASSOCIATES | 20.66 | 15.39 | 74.5 | 80
5 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/A WATER SUPPLY SCHEME | SM/14650 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 45 Cum., staging height 20 Mtr.) including by pass arrangement, guard room, chlorine room, pump house, CWR and boundary wall with other allied works for Augmentation of Mukutmanipur, Khatra & Ranibundh Zone- VII/A Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001767/2024-2025 | 490/BQA | 25/02/2025 | 26/10/2025 | BIKASH MANDAL | 8.91 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/A WATER SUPPLY SCHEME | SM/14650 | Augmentation | Work Order for Installation of scheme information board for 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- VII/A Water supply scheme (SM/14650), 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- VII/B Water supply scheme (SM/16936), 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- VIII/A Water supply scheme (SM/16261), 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- VIII/B Water supply scheme (SM/15003), 1 no. site of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme (SM/10295), 1 no. site of Augmentation of Banpukuria under Khatra-Hirbandh-Ranibandh Water Supply Scheme (SM/17123) within Ranibandh Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001913/2024-2025 | 157\KSD | 07/03/2025 | 17/03/2025 | S. B. CONSTRUCTION | 0.9 | 0 | 0 | 90
Total | [13 empty] | 36.89 | 17.8 | 48.26