## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/B WATER SUPPLY SCHEME | SM/15001 | Augmentation | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone 1B of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer |  | ORD/000235/2023-2024 | 1121/BMD | 24/05/2023 | 23/06/2023 | M/S DE ENGINEERING CONCERN | 2.28 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/B WATER SUPPLY SCHEME | SM/15001 | Augmentation | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-1B) (Sl. No. 02) |  | Junior Engineer | ORD/000624/2022-2023 | 180/KSD | 24/05/2022 | 08/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.06 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/B WATER SUPPLY SCHEME | SM/15001 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 5.91 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/B WATER SUPPLY SCHEME | SM/15001 | Augmentation | SOIL INVESTIGATION FOR PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN KHATRA SUB DIVITION OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 643/BQA | 24/03/2023 | 23/04/2023 | P. K. TEWARY DRILLING CO | 8.41 | 0 | 0 | 99
5 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/B WATER SUPPLY SCHEME | SM/15001 | Augmentation | Laying HDPE pipeline from Phulhari village to Damdi Village (Existing pipeline damaged due to widening of Dam inspection road at country side of Dam) with all allied works for Augmentation of Mukutmanipur, Khatra & Ranibundh (Zone- I/B) Water Supply Scheme under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001608/2023-2024 | 677/BQA | 27/02/2024 | 23/03/2024 | PRADYUMNA KOLEY | 5.95 | 0 | 0 | 90
6 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/B WATER SUPPLY SCHEME | SM/15001 | Augmentation | Laying HDPE pipeline near Mukutmanipur Bus Stand to Phulhari Village (Existing pipeline damaged due to widening of Dam inspection road at country side of Dam) with all allied works for Augmentation of Mukutmanipur, Khatra & Ranibundh (Zone- I/B) Water Supply Scheme under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001609/2023-2024 | 678/BQA | 27/02/2024 | 23/03/2024 | S. B. CONSTRUCTION | 7.05 | 0 | 0 | 90
7 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/B WATER SUPPLY SCHEME | SM/15001 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000200/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 6.31 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/B WATER SUPPLY SCHEME | SM/15001 | Augmentation | Khatra - Ambikanagar Road from Ch. 6.328 km to Ch. 6.443 km ,from Ch. 6.593 km to Ch. 6.828 km and from Ch. 8.725 km to Ch. 9.325 km, Restoration work damage by PHE Department for laying pipe line under Bankura High way Division in the district of Bankura. Augmentation of MKR(Zone-I/B)W/S Scheme (SM/15001) |  |  | BILL/01245/2024-2025 | BP-347/2024-25 | 03/10/2024 | 03/10/2024 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 21.13 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/B WATER SUPPLY SCHEME | SM/15001 | Augmentation | Khatra - Ambikanagar Road from Ch. 6.328 km to Ch. 6.443 km ,from Ch. 6.593 km to Ch. 6.828 km and from Ch. 8.725 km to Ch. 9.325 km, Restoration work damage by PHE Department for laying pipe line under Bankura High way Division in the district of Bankura. Augmentation of MKR(Zone-I/B)W/S Scheme (SM/15001) |  |  | BILL/01030/2024-2025 |  | 28/09/2024 | 28/09/2024 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 21.13 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/B WATER SUPPLY SCHEME | SM/15001 | Augmentation | Construction of 5 mtr. x 5 mtr. size new Staff Room with allied Works for Mukutmanipur, Khatra & Ranibandh (Zone- I/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000537/2022-2023 | 435/BQA | 06/03/2023 | 01/04/2026 | NAYAN BARDHAN | 8.66 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/B WATER SUPPLY SCHEME | SM/15001 | Augmentation | Construction of Boundary Wall with allied Works at Head Work site for Mukutmanipur, Khatra & Ranibandh (Zone- I/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000539/2022-2023 | 437/BQA | 06/03/2023 | 02/04/2025 | ASOKE KUMAR SAHU | 19.49 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/B WATER SUPPLY SCHEME | SM/15001 | Augmentation | Construction of Chlorine Room at OHR Site for Mukutmanipur, Khatra & Ranibandh (Zone- I/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000538/2022-2023 | 436/BQA | 06/03/2023 | 02/07/2025 | SOURAV SINHAMAHAPATRA | 4.63 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/B WATER SUPPLY SCHEME | SM/15001 | Augmentation | supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works, providing ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 100 m³ capacity R.C.C OHR (based on Departmental Design ) with 20 mtr staging height including foundation, pipeline connection and cost of pipes, specials etc. with allied worksfor Mukutmanipur, Khatra & Ranibundh (Zone- I/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000085/2023-2024 | 1062/BQA | 03/05/2023 | 24/06/2025 | GOUTAM BHATTACHRYYA | 200.64 | 0 | 0 | 30
Total | [13 empty] | 314.65 | 0 | 0