## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VIII/B WATER SUPPLY SCHEME | SM/15003 | Augmentation | Construction of 5 mtr. x 5 mtr. size new Staff Room with allied Works for Mukutmanipur, Khatra & Ranibandh (Zone- VII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000578/2022-2023 | 448/BQA | 06/03/2023 | 04/06/2023 | DURGADAS SINGHA | 8.65 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VIII/B WATER SUPPLY SCHEME | SM/15003 | Augmentation | Construction of Chlorine Room at OHR Site for Mukutmanipur, Khatra & Ranibandh (Zone- VIII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000591/2022-2023 | 452/BQA | 06/03/2023 | 25/04/2024 | ROY CHOWDHURY ENTERPRISE | 4.63 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VIII/B WATER SUPPLY SCHEME | SM/15003 | Augmentation | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-8B of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000245/2023-2024 | 1130/BMD | 24/05/2023 | 23/06/2023 | SUTRADHAR TRADERS | 2.39 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VIII/B WATER SUPPLY SCHEME | SM/15003 | Augmentation | Construction of Boundary Wall (Length- 130 Mtr.) with allied Works at Head Work site for Mukutmanipur, Khatra & Ranibandh (Zone- VIII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000517/2023-2024 | 2425/BQA | 22/08/2023 | 06/10/2023 | JALALUDDIN MOLLA | 19.49 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VIII/B WATER SUPPLY SCHEME | SM/15003 | Augmentation | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Ranibandh, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-8B) (Sl. No. 15) |  | Junior Engineer | ORD/000635/2022-2023 | 193/KSD | 24/05/2022 | 08/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.43 | 3.4 | 99.01 | 0
6 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VIII/B WATER SUPPLY SCHEME | SM/15003 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000047/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 0.55 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VIII/B WATER SUPPLY SCHEME | SM/15003 | Augmentation | SOIL INVESTIGATION FOR PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN KHATRA SUB DIVITION OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 643/BQA | 24/03/2023 | 23/04/2023 | P. K. TEWARY DRILLING CO | 8.41 | 0.84 | 10 | 99
8 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VIII/B WATER SUPPLY SCHEME | SM/15003 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000213/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 11.09 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VIII/B WATER SUPPLY SCHEME | SM/15003 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works, providing ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 350 m³ capacity R.C.C OHR (based on Departmental Design ) with 20 mtr staging height including foundation, pipeline connection and cost of pipes, specials etc. with allied worksfor Mukutmanipur, Khatra & Ranibundh (Zone- VIII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000116/2023-2024 | 1198/BQA | 22/05/2023 | 16/02/2024 | PRAVAT SARKAR | 367.98 | 139.72 | 37.97 | 40
10 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VIII/B WATER SUPPLY SCHEME | SM/15003 | Augmentation | Construction of Boundary Wall (Length- 130 Mtr.) with allied Works at Head Work site for Mukutmanipur, Khatra & Ranibandh (Zone- VII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001301/2023-2024 | 886/BQA | 12/03/2024 | 15/12/2025 | SWAPAN KUMAR UPADHYAY | 19.54 | 5.12 | 26.2 | 80
11 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VIII/B WATER SUPPLY SCHEME | SM/15003 | Augmentation | Crossing of Road at different location by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Mukutmanipur, Khatra & Ranibundh (Zone- VIII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000059/2024-2025 | 1488/BQA | 18/06/2024 | 02/08/2024 | SUBHADIP KOLE | 20.47 | 20.37 | 99.47 | 90
12 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VIII/B WATER SUPPLY SCHEME | SM/15003 | Augmentation | Construction of 5 mtr. x 5 mtr. size new Staff Room with allied Works for Mukutmanipur, Khatra & Ranibandh (Zone- VIII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000588/2022-2023 | 451/BQA | 06/03/2023 | 04/06/2023 | ASHIS PAL | 8.65 | 0 | 0 | 0
Total | [13 empty] | 475.28 | 169.44 | 35.65