## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/A WATER SUPPLY SCHEME | SM/15005 | Augmentation | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-3A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer |  | ORD/000459/2023-2024 | 1785/BMD | 01/08/2023 | 30/09/2023 | M/S DE ENGINEERING CONCERN | 2.39 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/A WATER SUPPLY SCHEME | SM/15005 | Augmentation | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-3A) (Sl. No. 05) |  | Junior Engineer | ORD/000627/2022-2023 | 183/KSD | 24/05/2022 | 08/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.09 | 3.21 | 78.55 | 0
3 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/A WATER SUPPLY SCHEME | SM/15005 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 26 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/A WATER SUPPLY SCHEME | SM/15005 | Augmentation | Work order for Crossing of Road at different location by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Mukutmanipur, Khatra & Ranibundh (Zone- III/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000178/2024-2025 | 1837/BQA | 12/07/2024 | 26/08/2024 | SIBSANKAR CHOWDHURY | 14.17 | 14.1 | 99.5 | 80
5 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/A WATER SUPPLY SCHEME | SM/15005 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000203/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 15.88 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/A WATER SUPPLY SCHEME | SM/15005 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone‐ III/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( SM/15005 ) |  |  | BILL/01242/2024-2025 | BP-226/2024-25 | 13/08/2024 | 13/08/2024 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 45.36 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/A WATER SUPPLY SCHEME | SM/15005 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone- III/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000080/2023-2024 | 974/BQA | 28/04/2023 | 31/12/2024 | S.N POLYMERS PVT LTD | 312.82 | 114.31 | 36.54 | 65
8 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/A WATER SUPPLY SCHEME | SM/15005 | Augmentation | Work Order for Emergency laying of pipeline from Rajapara More to Khatra Police Station (left side of the road) [due to construction of cement concrete road from Rajapara more to Khatra Puratan Bazar and Khatra Puratan Bazar to Kharban More (Partly renovation work of the Bituminous road)] to provide FHTC under Augmentation of Mukutmanipur, Khatra & Ranibundh Water Supply Scheme (Zone-III/A) under Jal Jeevan Mission programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002284/2024-2025 | 58\KSD | 16/01/2025 | 26/01/2025 | S.N POLYMERS PVT LTD | 5.63 | 0 | 0 | 95
9 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/A WATER SUPPLY SCHEME | SM/15005 | Augmentation | Work Order for Emergency laying of pipeline from Rajapara More to Khatra Police Station (right side of the road) [due to construction of cement concrete road from Rajapara more to Khatra Puratan Bazar and Khatra Puratan Bazar to Kharban More (Partly renovation work of the Bituminous road)] to provide FHTC under Augmentation of Mukutmanipur, Khatra & Ranibundh Water Supply Scheme (Zone-III/A) under Jal Jeevan Mission programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002285/2024-2025 | 59\KSD | 16/01/2025 | 26/01/2025 | S.N POLYMERS PVT LTD | 5.46 | 0 | 0 | 95
10 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/A WATER SUPPLY SCHEME | SM/15005 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone‐ III/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( SM/15005 ) |  |  | BILL/00659/2024-2025 |  | 09/08/2024 | 09/08/2024 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 45.36 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/A WATER SUPPLY SCHEME | SM/15005 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 450 Cum., staging height 20 Mtr.) including by pass arrangement, construction of boundary wall and repairing of guard room for Augmentation of Mukutmanipur, Khatra & Ranibundh Zone- III/A Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001765/2024-2025 | 488/BQA | 25/02/2025 | 02/03/2026 | TAPAS PAL | 24.51 | 0 | 0 | 100
Total | [13 empty] | 501.66 | 131.62 | 26.24