## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/A WATER SUPPLY SCHEME | SM/15005 | Augmentation | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-3A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer |  | ORD/000459/2023-2024 | 1785/BMD | 01/08/2023 | 30/09/2023 | M/S DE ENGINEERING CONCERN | 2.39 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/A WATER SUPPLY SCHEME | SM/15005 | Augmentation | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-3A) (Sl. No. 05) |  | Junior Engineer | ORD/000627/2022-2023 | 183/KSD | 24/05/2022 | 08/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.09 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/A WATER SUPPLY SCHEME | SM/15005 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 26 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/A WATER SUPPLY SCHEME | SM/15005 | Augmentation | Work order for Crossing of Road at different location by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Mukutmanipur, Khatra & Ranibundh (Zone- III/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000178/2024-2025 | 1837/BQA | 12/07/2024 | 26/08/2024 | SIBSANKAR CHOWDHURY | 14.17 | 0 | 0 | 80
5 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/A WATER SUPPLY SCHEME | SM/15005 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000203/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 15.88 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/A WATER SUPPLY SCHEME | SM/15005 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone‐ III/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( SM/15005 ) |  |  | BILL/01242/2024-2025 | BP-226/2024-25 | 13/08/2024 | 13/08/2024 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 45.36 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/A WATER SUPPLY SCHEME | SM/15005 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone- III/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000080/2023-2024 | 974/BQA | 28/04/2023 | 31/12/2024 | S.N POLYMERS PVT LTD | 312.82 | 0 | 0 | 65
Total | [13 empty] | 420.71 | 0 | 0