## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/A WATER SUPPLY SCHEME | SM/15006 | Augmentation | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-4A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000247/2023-2024 | 1131/BMD | 24/05/2023 | 23/06/2023 | M/S DAS & SARKAR ENTERPRISE | 2.39 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/A WATER SUPPLY SCHEME | SM/15006 | Augmentation | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-4A) (Sl. No. 07) |  | Junior Engineer | ORD/000628/2022-2023 | 185/KSD | 24/05/2022 | 08/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.31 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/A WATER SUPPLY SCHEME | SM/15006 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000205/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 3.75 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/A WATER SUPPLY SCHEME | SM/15006 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone- IV/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer (Contractual) | ORD/000536/2022-2023 | 432/BQA | 06/03/2023 | 04/06/2023 | PRADIP CHAKRABORTY | 82.63 | 0 | 0 | 85
5 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐IV/A WATER SUPPLY SCHEME | SM/15006 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 100 Cum., staging height 20 Mtr.) including by pass arrangement, guard room, boundary wall and laying distribution pipeline with other allied works for Augmentation of Mukutmanipur, Khatra & Ranibundh Zone- IV/A Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000221/2025-2026 | 1421/BQA | 26/06/2025 | 24/09/2025 | ASOKE KUMAR SAHU | 54.02 | 0 | 0 | 0
Total | [13 empty] | 146.09 | 0 | 0