## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME | SM/15008 | Augmentation | Acceptance cum Formal work order for the work of Providing & installation of Pumping machineries with other electro-mechanical accessories for OHR site Zone-2A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000458/2023-2024 | 1784/BMD | 01/08/2023 | 29/11/2023 | S P ENTERPRISE (SILIGURI) | 26.41 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME | SM/15008 | Augmentation | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-2A) (Sl. No. 03) |  | Junior Engineer | ORD/000625/2022-2023 | 181/KSD | 24/05/2022 | 08/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.44 | 3.05 | 88.71 | 0
3 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME | SM/15008 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 3.64 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME | SM/15008 | Augmentation | Construction of CWR & Pump House at OHR site under Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- II/A Water supply scheme under Khatra Sub- Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001146/2023-2024 | 351/BQA | 05/02/2024 | 04/06/2024 | GOUR GORAI | 20.72 | 19.93 | 96.23 | 50
5 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME | SM/15008 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000201/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 5.9 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME | SM/15008 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone- II/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000078/2023-2024 | 972/BQA | 28/04/2023 | 02/04/2025 | GOUTAM BHOWMIK | 166.52 | 104.87 | 62.98 | 40
7 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME | SM/15008 | Augmentation | Work Order for Installation of scheme information board for 2 nos. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- II/A Water supply scheme (SM/15008), 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- II/B Water supply scheme (SM/15002), 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- III/A Water supply scheme (SM/15005), 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- III/B Water supply scheme (SM/18495) and 1 no. site of Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- IV/A Water supply scheme (SM/15006) within Khatra Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001909/2024-2025 | 153\KSD | 07/03/2025 | 17/03/2025 | SRIJAN CONSTRUCTION | 0.9 | 0 | 0 | 90
Total | [13 empty] | 227.52 | 127.85 | 56.19