## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME | SM/15008 | Augmentation | Acceptance cum Formal work order for the work of Providing & installation of Pumping machineries with other electro-mechanical accessories for OHR site Zone-2A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000458/2023-2024 | 1784/BMD | 01/08/2023 | 29/11/2023 | S P ENTERPRISE (SILIGURI) | 26.41 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME | SM/15008 | Augmentation | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-2A) (Sl. No. 03) |  | Junior Engineer | ORD/000625/2022-2023 | 181/KSD | 24/05/2022 | 08/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.44 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME | SM/15008 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 3.64 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME | SM/15008 | Augmentation | Construction of CWR & Pump House at OHR site under Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- II/A Water supply scheme under Khatra Sub- Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001146/2023-2024 | 351/BQA | 05/02/2024 | 04/06/2024 | GOUR GORAI | 20.72 | 0 | 0 | 50
5 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME | SM/15008 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000201/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 5.9 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME | SM/15008 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 135 Cum., staging height 20 Mtr.) including by pass arrangement, guard room, boundary wall with other allied works for Augmentation of Mukutmanipur, Khatra & Ranibundh Zone- II/A Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001762/2024-2025 | 487/BQA | 25/02/2025 | 11/11/2025 | PARTHA SARATHI PATRA | 10.43 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME | SM/15008 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone- II/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000078/2023-2024 | 972/BQA | 28/04/2023 | 02/04/2025 | GOUTAM BHOWMIK | 166.52 | 0 | 0 | 40
Total | [13 empty] | 237.05 | 0 | 0