## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Kotulpur | Bankura Division | Jibta Piped Water Supply Scheme | SM/15018 | New | Material Requisition To Resource Division |  |  | RTOR000086/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 31.95 | 0 | 0 | 0
2 | BANKURA | Kotulpur | Bankura Division | Jibta Piped Water Supply Scheme | SM/15018 | New | Material Requisition To Resource Division |  |  | RTOR000009/2024-2025 | 2011/BQA | 26/07/2024 | 26/07/2024 | Resource Division | 5.52 | 0 | 0 | 0
3 | BANKURA | Kotulpur | Bankura Mechanical | Jibta Piped Water Supply Scheme | SM/15018 | New | Jibta Piped Water Supply Scheme |  |  | BILL/01501/2023-2024 | BP-2023-24-96 | 15/02/2024 | 15/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 14.55 | 0 | 0 | 0
4 | BANKURA | Kotulpur | Bankura Mechanical | Jibta Piped Water Supply Scheme | SM/15018 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Jibta piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Kotulpur, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000112/2023-2024 | 771/BMD | 24/04/2023 | 01/05/2025 | ABHIJIT MUKHERJEE | 31.26 | 0 | 0 | 64
Total | [13 empty] | 83.27 | 0 | 0