## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Patrasayer | Bankura Division | Dhagaria Piped Water Supply Scheme | SM/15023 | New | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 26.98 | 0 | 0 | 0
2 | BANKURA | Patrasayer | Bankura Division | Dhagaria Piped Water Supply Scheme | SM/15023 | New | Material Requisition To Resource Division |  |  | RTOR000010/2024-2025 | 2011/BQA | 26/07/2024 | 26/07/2024 | Resource Division | 11.4 | 0 | 0 | 0
3 | BANKURA | Patrasayer | Bankura Mechanical | Dhagaria Piped Water Supply Scheme | SM/15023 | New | Dhagaria Piped Water Supply Scheme |  |  | BILL/01670/2023-2024 | BP-2023-24-182 | 22/03/2024 | 22/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 18.51 | 0 | 0 | 0
4 | BANKURA | Patrasayer | Bankura Division | Dhagaria Piped Water Supply Scheme | SM/15023 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR DHAGARIA PIPED WATER SUPPLY SCHEME, BLOCK- PATRASAYER, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000347/2023-2024 | 1971/BQA | 18/07/2023 | 02/10/2025 | BAJRANG ROAD CONSTRUCTION PRIVATE LIMITED | 534.2 | 194.99 | 36.5 | 70
5 | BANKURA | Patrasayer | Bankura Mechanical | Dhagaria Piped Water Supply Scheme | SM/15023 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Dhagaria Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000035/2025-2026 | 240/BMD | 14/05/2025 | 12/08/2025 | M/S SOMA ENTERPRISES | 11.67 | 0 | 0 | 0
Total | [13 empty] | 602.76 | 194.99 | 32.35