## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission. | SM/15258 | Support-WQMSP | Uploading charges of drinking Water samples tested through FTKs related to Water Quality Monitoring & Surveillance Programme under Bankura-II,Barjora, Chhatna, Saltora, Gangajalghati & Mejia block Bankura Division PHE Dte. (Part-C) | Assistant Engineer |  | ORD/000256/2023-2024 | 137/BK | 08/06/2023 | 23/06/2023 | ABHIRUP MALLA | 0.97 | 0.97 | 100 | 100
2 | BANKURA |  | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission. | SM/15258 | Support-WQMSP | Uploading charges of drinking Water samples tested through FTKs related to Water Quality Monitoring & Surveillance Programme under Bankura-I, Onda, Bishnupur, Joypur, Kotulpur, Indus, Patrasayer & Sonamukhi block under Bankura Division PHE Dte.(Part-B) | Assistant Engineer |  | ORD/000255/2023-2024 | 136/BK | 30/06/2023 | 15/07/2023 | ABHIRUP MALLA | 0.97 | 0.97 | 100 | 100
3 | BANKURA |  | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission. | SM/15258 | Support-WQMSP | Uploading charges of drinking Water samples tested through FTKs related to Water Quality Monitoring & Surveillance Programme under Hirbandh, Indpur, Khatra,Ranibandh,Raipur, Sarenga, Simlapal & Taldangra block Bankura Division PHE Dte. (Part-A) | Assistant Engineer |  | ORD/000254/2023-2024 | 135/BK | 08/06/2023 | 23/06/2023 | ABHIRUP MALLA | 0.97 | 0.97 | 100 | 100
4 | BANKURA |  | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission. | SM/15258 | Support-WQMSP | Work order for Shifting of different materials Like FTKs (Fe,FRC,Bacteria, pH, TDS,Turbidity & Fluoride) including Training Manuals, Data Record Sheet Book & Bags for carrying kits from Office of The Assistant Engineer ,R.W.S Bankura Sub-Division P.H.E. Dte. to Kotulpur, Khatra, Simlapal, Chhatna & Sonamukhi B.M.O.H Office under Bankura District (Sl No.-04) | Assistant Engineer | Junior Engineer | ORD/001344/2023-2024 | 55/BK | 04/03/2024 | 11/03/2024 | ABHIRUP MALLA | 0.09 | 0.09 | 100 | 95
5 | BANKURA |  | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission. | SM/15258 | Support-WQMSP | Work order for Shifting of different materials Like FTKs (Fe, FRC, Bacteria, pH, TDS, Turbidity & Fluoride) including Training Manuals, Data Record Sheet Book & Bags for carrying kits from Office of The Assistant Engineer ,R.W.S Bankura Sub-Division P.H.E. Dte. to Raipur, Hirbandh, Saltora & Bishnupur B.M.O.H Office under Bankura District (Sl No.-03) | Assistant Engineer | Junior Engineer | ORD/001331/2023-2024 | 54/BK | 04/03/2024 | 11/03/2024 | ABHIRUP MALLA | 0.09 | 0.09 | 100 | 95
6 | BANKURA |  | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission. | SM/15258 | Support-WQMSP | Work order for Shifting of different materials Like FTKs (Fe,FRC,Bacteria, pH, TDS & Turbidity ) including Training Manuals, Data Record Sheet Book & Bags for carrying kits from Office of The Assistant Engineer ,R.W.S Bankura Sub-Division P.H.E. Dte. to Ranibandh, Indus, Bankura-I, Bankura-II & Onda B.M.O.H Office under Bankura District (Sl No.-02) | Assistant Engineer | Junior Engineer | ORD/001330/2023-2024 | 53/BK | 04/03/2024 | 11/03/2024 | ABHIRUP MALLA | 0.09 | 0.09 | 100 | 95
7 | BANKURA |  | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission. | SM/15258 | Support-WQMSP | Distribution of Field Test Kit(FTKs) to different B.M.O.H office .(sl. no. -02) |  |  | BILL/00341/2025-2026 |  | 02/06/2025 | 02/06/2025 | TAPAS DEY | 0.1 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission. | SM/15258 | Support-WQMSP | Distribution of Field Test Kit(FTKs) to different B.M.O.H office .(sl. no. -04) |  |  | BILL/00326/2025-2026 |  | 21/05/2025 | 21/05/2025 | TAPAS DEY | 0.09 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission. | SM/15258 | Support-WQMSP | Distribution of Field Test Kit(FTKs) to different B.M.O.H office .(sl. no. -01) |  |  | BILL/00325/2025-2026 |  | 21/05/2025 | 21/05/2025 | TAPAS DEY | 0.09 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission. | SM/15258 | Support-WQMSP | Distribution of Field Test Kit(FTKs) to different B.M.O.H office .(sl. no. -03) |  |  | BILL/00342/2025-2026 |  | 02/06/2025 | 02/06/2025 | TAPAS DEY | 0.1 | 0 | 0 | 0
Total | [13 empty] | 3.57 | 3.19 | 89.25