## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | Repairing and renovation of bankura district Labortary under Bankura Division, P.H.E.Dte ( Part-I ) |  | Junior Engineer | ORD/000011/2023-2024 | 760/BQA | 04/04/2023 | 03/06/2023 | GANESH ROY | 3.71 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | Upgradation of Water Testing Laboratory of Simlapal Sub District Water Testing Laboratory (Chhoto Sarenga Labour contract & constructive society Ltd) under Bankura Division, P.H.E.Dte. ( Annexure-II) |  | Junior Engineer | ORD/000007/2023-2024 | 756/BQA | 04/04/2023 | 03/06/2023 | TAPAS DEY | 5.53 | 0 | 0 | 50
3 | BANKURA |  | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | Repairing and renovation of Bankura District Labortary under Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000651/2022-2023 | 27/A/BK | 23/02/2023 | 23/03/2023 | TAPAS DEY | 0.58 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | Supply & Installation 1.5 Ton split A.C for Bacteriological Room at Bankura District Laboratory under Bankura Division, P.H.E. Dte. (Sl No.- 01) |  | Junior Engineer | ORD/000653/2022-2023 | 32/BK | 06/03/2023 | 21/03/2023 | TAPAS DEY | 0.52 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | Supply & Installation 1.5 Ton split A.C for Chemical Room at Bankura District Laboratory under Bankura Division, P.H.E. Dte. (Sl No.- 02) |  | Junior Engineer | ORD/000655/2022-2023 | 34/BK | 06/03/2023 | 21/03/2023 | TAPAS DEY | 0.52 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | Supply & Installation 1.5 Ton split A.C for Wet Laboratory Room at Bankura District Laboratory under Bankura Division, P.H.E. Dte. (Sl No.- 03) |  | Junior Engineer | ORD/000665/2022-2023 | 37/BK | 10/03/2023 | 25/03/2023 | TAPAS DEY | 0.52 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | Submission of U.C for the lab contegency month of January 2022 of March 2022 |  |  | BILL/01144/2023-2024 | FHTC/10 | 04/10/2023 | 04/10/2023 | SONAMUKHI BIKALPA UNNAYAN SAMITY | 0.08 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | submission of U.C for the lab contegency month of april 2022 to may 2022 |  |  | BILL/01252/2023-2024 | FHTC/10 | 12/10/2023 | 12/10/2023 | SONAMUKHI BIKALPA UNNAYAN SAMITY | 0.09 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | Prayer for release fund for laboratory personal's puja Festival's Bonus for the year 2022 |  |  | BILL/00306/2023-2024 | FHTC/06 | 02/06/2023 | 02/06/2023 | HIJALDIHA VIVEKANANDA SEVA SAMITY | 0.14 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | water testing laboratoryof our samity (BTMSKS) for administrative expenses for the month of January 2023 to March 2023 |  |  | BILL/00307/2023-2024 |  | 25/05/2023 | 25/05/2023 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 1.5 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | Submission of U.C For The Lab Contegency Month of (April 2022 to May 2022) |  |  | BILL/01170/2023-2024 |  | 03/10/2023 | 03/10/2023 | SONAMUKHI BIKALPA UNNAYAN SAMITY | 0.09 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | water testing laboratory of our samity (BTMSKS) for administrative expense for the month of January 2023 to march 2023 |  |  | BILL/00608/2023-2024 | FHTC/06 | 02/06/2023 | 02/06/2023 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.15 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | Payment of laboratory staff of the month May 2023 to August 2023 |  |  | BILL/01147/2023-2024 | FHTC/10 | 04/10/2023 | 04/10/2023 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 1.8 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | Administrative expenses of water testing laboratory of our samity (BTMSKS) of the month April 2023 |  |  | BILL/01145/2023-2024 | FHTC/10 | 04/10/2023 | 04/10/2023 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.04 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | payment of laboratory staff for the month of january 2023 to march 2023 |  |  | BILL/00079/2023-2024 | FHTC/06 | 02/06/2023 | 02/06/2023 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 1.35 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | Administrative expenses of water testing laboratory of our samity (BTMSKS) of the month May 2023 to August 2023 |  |  | BILL/01148/2023-2024 | FHTC/10 | 04/10/2023 | 04/10/2023 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.2 | 0 | 0 | 0
17 | BANKURA |  | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | payment for laboratory staff of the month April 2023 |  |  | BILL/01251/2023-2024 | FHTC/10 | 12/10/2023 | 12/10/2023 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.45 | 0 | 0 | 0
18 | BANKURA |  | Bankura Mechanical | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | Acceptance cum Formal work order for the work of Electrical and illumination works related to instruments and laboratory requirement for prosed water testing laboratory at P.H.E Dte Kanchanpur OHR site , Bankura under Bankura Mechanical Division PHE, Dte. | Assistant Engineer | Junior Engineer | ORD/000196/2023-2024 | 1019/BMD | 22/05/2023 | 21/07/2023 | CHAKRABORTY MINING & ENGINEERING. | 8.54 | 0 | 0 | 70
19 | BANKURA |  | Bankura Mechanical | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | Acceptance cum Formal work order for the work of Name Electrical and illumination works related to instruments and laboratory requirement for proposed water testing laboratory at Simlapal BPHC campus, Bankura under Bankura Mechanical Division PHE, Dte. | Assistant Engineer | Junior Engineer | ORD/000197/2023-2024 | 1020/BMD | 22/05/2023 | 21/07/2023 | M/S DAS & SARKAR ENTERPRISE | 8.55 | 0 | 0 | 60
20 | BANKURA |  | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | Improvement of water testing laboratory building for Bankura-II Sub District water testing Laboratory (Mallabhum Mahila Kalyan Samity) at Tilabedia OHR site of Bankura -II Block under RWS Bankura Sub- Division under Bankura Division P.H.E. Dte. ( Annexure-I) | Assistant Engineer | Junior Engineer | ORD/000016/2023-2024 | 758/BQA | 04/04/2023 | 03/06/2023 | GOUR GORAI | 12.05 | 0 | 0 | 25
21 | BANKURA |  | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | Improvement of Joypur Sub District Laboratory (Hijaldiha Vivekananda Seva Samity) at Joypur OHR/Headwork Site Campus under Bankura Division PHE Dte. ( Annexure-IV) | Assistant Engineer | Junior Engineer | ORD/000008/2023-2024 | 757/BQA | 04/04/2023 | 03/06/2023 | GANGADHAR MONDAL | 17.92 | 0 | 0 | 70
22 | BANKURA |  | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | IMPROVEMENT OF INDPUR SUB-DISTRICT LABAROTARY AT JAMBEDIYA WATER SUPPLY SCHEME UNDER BANKURA DIVISION PHE DTE. UNDER JAL JEEVAN MISSION. ( Annexure-V). | Assistant Engineer | Junior Engineer | ORD/000010/2023-2024 | 759/BQA | 04/04/2023 | 03/06/2023 | SAYED PAHALOWAN | 24.03 | 0 | 0 | 97
23 | BANKURA |  | Bankura Mechanical | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | Acceptance cum Formal work order for the work of Electrical and illumination works related to instruments and laboratory requirement for proposed water testing laboratory at P.H.E Dte OHR site, Joypur water supply scheme, Bankura under Bankura Mechanical Division PHE, Dte. | Assistant Engineer | Junior Engineer | ORD/000195/2023-2024 | 1018/BMD | 22/05/2023 | 21/07/2023 | SUTRADHAR TRADERS | 8.55 | 0 | 0 | 80
24 | BANKURA |  | Bankura Mechanical | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | Acceptance cum Formal work order for the work of Electrical and illumination works related to instruments and laboratory requirement for proposed Water Testing Laboratory at PHED OHR site, Jambedia of Indpur Sub-District Laboratory under Bankura Mechanical Division PHE, Dte. | Assistant Engineer | Junior Engineer | ORD/000194/2023-2024 | 1017/BMD | 22/05/2023 | 21/07/2023 | KASHINATH DEY | 8.56 | 0 | 0 | 100
25 | BANKURA |  | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | Repairing and Renovation Work of an existing damaged PHE Dte. quarter in connection with sifting of Sonamukhi Sub District Water Testing Laboratory (Formerly Sonamukhi Bikalpa Unnayan Samity) at Sonamukhi Water Supply Scheme Campus, Sonamukhi, Bankura (Door Window Painting, Rack & Table Covering by ACP Pannel, Sanitary, Plumbing, Water Supply, Electrification, Furniture Purchase Work) (Sl No.- 02) | Assistant Engineer |  | ORD/001093/2022-2023 | 17/BK | 08/02/2023 | 08/04/2023 | BIT ENTERPRISE | 3.72 | 0 | 0 | 10
26 | BANKURA |  | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. | SM/15259 | Support-WQMSP | Repairing and Renovation Work of an existing damaged PHE Dte. quarter in connection with sifting of Sonamukhi Sub District Water Testing Laboratory (Formerly Sonamukhi Bikalpa Unnayan Samity) at Sonamukhi Water Supply Scheme Campus, Sonamukhi, Bankura (Dismentling, Dam Proofing, Crack Repairing, Re-Plastering, Flooring, Inside Outside Wall Painting Work) (Sl No.- 01) | Assistant Engineer |  | ORD/001082/2022-2023 | 15/BK | 07/02/2023 | 07/04/2023 | BIT ENTERPRISE | 4.51 | 0 | 0 | 10
Total | [13 empty] | 113.69 | 0 | 0