## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Continuation work order for providing services for operation of 10 (ten) nos Laboratory under Bankura Division, P.H.E.Dte. for the period from 01.05.2022 to 31.10.2022 i.e.06 (Six) months. |  | Junior Engineer | ORD/000321/2022-2023 | 901/BQA | 18/04/2022 | 24/04/2022 | CLIFFORD FACILITY SERVICES PVT. LTD. | 19.78 | 10.54 | 53.28 | 0
2 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Continuation Work order for Providing services for operation of 10 (Ten) nos. laboratory under Bankura Division PHE Dte. for the period from 01.05.2022 to 31.10.2022 i.e. 06 (Six) months. |  | Junior Engineer | ORD/000656/2022-2023 | 2079/BQA | 21/10/2022 | 21/04/2023 | CLIFFORD FACILITY SERVICES PVT. LTD. | 18.48 | 18.48 | 100 | 0
3 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Providing services for operation of 03 (three) nos Laboratory under Bankura Division, P.H.E.Dte. for the period from 11.07.2022 to 30.06.2023 i.e.12 ( twelve) months. | Assistant Engineer | Junior Engineer | ORD/000331/2022-2023 | 1530 /BQA | 08/07/2022 | 08/07/2023 | CLIFFORD FACILITY SERVICES PVT. LTD. | 16.14 | 15.71 | 97.34 | 50
4 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Supply of different Chemicals, sample container etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. (Sl No.- 01) | Assistant Engineer |  | ORD/000248/2023-2024 | 69/BK | 25/04/2023 | 25/05/2023 | SONU SINGH | 0.96 | 0.96 | 100 | 0
5 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Supply of different Chemicals,sample container etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. (Sl No.- 02) | Assistant Engineer |  | ORD/000530/2023-2024 | 70/BK | 25/04/2023 | 25/05/2023 | ABHIRUP MALLA | 0.95 | 0.95 | 100 | 30
6 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Supply of different Chemicals, Membrane Filter, DPD tablet, Biosol etc. for 16 nos Water Testing Laboratories of Bankura RWS Sub -Division under Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/000774/2023-2024 | 232/BK | 12/10/2023 | 12/11/2023 | LAXMI ENTERPRISE | 3.53 | 3.53 | 100 | 96
7 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Supply of different Chemicals, Manganese, Ferospectral Reagent etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. (Sl No. -01) | Assistant Engineer |  | ORD/001077/2022-2023 | 47/A/BK | 24/03/2023 | 08/04/2023 | SUBHADIP KOLEY | 4.33 | 4.33 | 100 | 10
8 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Supply of different chemicals, reagents for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/000667/2023-2024 | 134/BK | 07/06/2023 | 07/07/2023 | LAB SOLUTION | 4.38 | 4.38 | 100 | 30
9 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Supply of different Chemicals, Manganese, Ferospectral Reagent etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/000771/2023-2024 | 231/BK | 12/10/2023 | 12/11/2023 | LAXMI ENTERPRISE | 3.7 | 3.7 | 100 | 98
10 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Supply of different Chemicals, Manganese, Ferospectral Reagent etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. (Sl No. -02) | Assistant Engineer |  | ORD/001073/2022-2023 | 48/BK | 24/03/2023 | 08/04/2023 | SUBHADIP KOLEY | 4.61 | 4.61 | 100 | 10
11 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Work order for procurement of necessary Chemicals/reagents for available chlorine & chlorine demand testing purpose of Laboratories under Bankura Division , P.H.E. Dte. | Assistant Engineer |  | ORD/001023/2023-2024 | 213/BK | 22/09/2023 | 22/10/2023 | SONU SINGH | 0.97 | 0.97 | 100 | 95
12 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Providing services for operation of 10 (ten) nos Laboratory w.e.f.01.06.2023 to 30.04.2024 & 03 ( Three) nos.Laboratory w.e.f.01.06.2023 to 30.04.2024 under Bankura Division, P.H.E.Dte. (SL.NO-01) | Assistant Engineer | Junior Engineer | ORD/000137/2023-2024 | 1306/BQA | 30/05/2023 | 29/05/2024 | CLIFFORD FACILITY SERVICES PVT. LTD. | 74.67 | 72.57 | 97.19 | 98
13 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Work order for Maintenance Of Computer Of 09 ( Nine) Nos. PHED Laboratories (Patrasayer Sub District Lab, Bishnupur Sub District Lab, Onda Sub District Lab, Taldangra Sub District Lab, Raipur Sub District Lab , Sanabandh Sub District Lab , Sarberia Sub District Lab, Saltora Sub District Lab & G.Ghati Sub District Lab) in the district of Bankura under Bankura Division, P.H.E. Dte. for the period from 01/07/2023 to 30/09/2023 (Three Months). | Assistant Engineer |  | ORD/001017/2023-2024 | 161\BK | 30/06/2023 | 30/09/2023 | TAPAS DEY | 0.34 | 0.34 | 100 | 98
14 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Work order for Annual Maintenance Contract for computers Printers, UPS and other related peripherals for Bankura District Laboratory , Mukutmanipur WTP Laboratory and 05 Nos NGO Managed Laboratories under Bankura Division PHE Dte. w.e.f. 01.06.2023 to 30.09.2023 . | Assistant Engineer |  | ORD/001021/2023-2024 | 131/BK | 31/05/2023 | 30/09/2023 | TAPAS DEY | 0.42 | 0.41 | 98.87 | 98
15 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Procurement of necessary Chemicals/reagents for available chlorine & chlorine demand testing purpose of Laboratories under Bankura Division , P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001132/2023-2024 | 214\BK | 22/09/2023 | 22/10/2023 | ABHIRUP MALLA | 0.97 | 0.97 | 100 | 100
16 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Work order for Supervision and extend support to NABL recognized Water Quality Testing Sub District Laboratory i.e. Onda sub district water testing Laboratory under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site surveillance by NABL for a period of month from the date of commencement. | Assistant Engineer | Junior Engineer | ORD/001572/2023-2024 | 281/BK | 29/12/2023 | 29/02/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 80
17 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Work order for Supervision and extend support to NABL recognized Water Quality Testing Sub District Laboratory i.e. Mukutmanipur WTP sub district water testing Laboratory under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site surveillance by NABL for a period of month from the date of commencement. (Sl NO.-02) | Assistant Engineer | Junior Engineer | ORD/001571/2023-2024 | 280/BK | 29/12/2023 | 29/02/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
18 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Work order for Supervision and extend support to NABL recognized Water Quality Testing Sub District Laboratory i.e. Bishnupur under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site surveillance by NABL for a period of month from the date of commencement. | Assistant Engineer | Junior Engineer | ORD/001581/2023-2024 | 287\BK | 29/12/2023 | 29/02/2024 | DULAL MAJUMDER | 0.9 | 0.9 | 100 | 100
19 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Work order for Supervision and extend support to NABL recognized Water Quality Testing Sub District Laboratory i.e. Taldangra sub district water testing Laboratory under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site surveillance by NABL for a period of month from the date of commencement. (Sl NO.-01) | Assistant Engineer | Junior Engineer | ORD/001570/2023-2024 | 279/BK | 29/12/2023 | 29/02/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
20 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Work order for Supervision and extend support to NABL recognized Water Quality Testing Sub District Laboratory i.e. Saltora sub district water testing Laboratory under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site surveillance by NABL for a period of month from the date of commencement. | Assistant Engineer | Junior Engineer | ORD/001574/2023-2024 | 283\BK | 29/12/2023 | 29/02/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 95
21 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Work order for Supervision and extend support to NABL recognized Water Quality Testing Sub District Laboratory i.e. Raipur sub district water testing Laboratory under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site surveillance by NABL for a period of month from the date of commencement. | Assistant Engineer | Junior Engineer | ORD/001575/2023-2024 | 284\BK | 29/12/2023 | 29/02/2024 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
22 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Work order for Supervision and extend support to NABL recognized Water Quality Testing Sub District Laboratory i.e. Sarberia sub district water testing Laboratory under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site surveillance by NABL for a period of month from the date of commencement. | Assistant Engineer | Junior Engineer | ORD/001577/2023-2024 | 286\BK | 29/12/2023 | 29/02/2024 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 95
23 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Work order for Supervision and extend support to NABL recognized Water Quality Testing Sub District Laboratory i.e. Gangajalghati sub district water testing Laboratory under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site surveillance by NABL for a period of month from the date of commencement. | Assistant Engineer | Junior Engineer | ORD/001578/2023-2024 | 288\BK | 29/12/2023 | 29/02/2024 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
24 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Supply of different Chemicals, Reagent, Membrane Filter etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/001084/2023-2024 | 192/BQA | 22/01/2024 | 01/02/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 10.02 | 10.02 | 100 | 98
25 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Work order for Supply of Sample container, Chemicals etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/001352/2023-2024 | 75\BK | 13/03/2024 | 28/03/2024 | SONU SINGH | 0.96 | 0.96 | 100 | 98
26 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Work order for Supply of Sample container, Chemicals etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. ( Sl No.-1) | Assistant Engineer | Junior Engineer | ORD/001351/2023-2024 | 43/BK | 21/02/2024 | 07/03/2024 | TAPAS DEY | 0.96 | 0.96 | 100 | 100
27 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Continuation work order for Annual Maintenance Contract for computers Printers, UPS and other related peripherals for Bankura District Laboratory , Joypur, Indpur, Mukutmanipur WTP Site, Bankura-II, Simlapal, Sonamukhi, Patrasayer, Bishnupur, Sarberia, Gangajalghati, Sanabandh, Onda, Raipur, Saltora & Taldangra Sub District water testing Laboratory under Bankura Division PHE Dte. w.e.f. 01.10.2024 to 31.03.2025 . (Six Months) | Assistant Engineer | Junior Engineer | ORD/000415/2024-2025 | 227/A/BK | 27/09/2024 | 27/03/2025 | TAPAS DEY | 0.96 | 0 | 0 | 98
28 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Prayer for release fund for laboratory persoanal's Puja Festival's Bonus for the year 2023. |  |  | BILL/02579/2023-2024 |  | 05/03/2024 | 05/03/2024 | HIJALDIHA VIVEKANANDA SEVA SAMITY | 0.16 | 0 | 0 | 0
29 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/15260 | Support-WQMSP | Prayer for release fund for laboratory personal for the month of July 2023 to september 2023 |  |  | BILL/02468/2023-2024 | FHTC/02 | 09/02/2024 | 09/02/2024 | HIJALDIHA VIVEKANANDA SEVA SAMITY | 1.35 | 0 | 0 | 0
Total | [13 empty] | 175.85 | 161.6 | 91.9