## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VIII A WATER SUPPLY SCHEME | SM/16261 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Pumping machineries with other electro-mechanical accessories for OHR site Zone-8A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 1120/BMD | 24/05/2023 | 08/07/2023 | AMITAVA CHAKRABORTY | 26.24 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VIII A WATER SUPPLY SCHEME | SM/16261 | Augmentation | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Ranibandh, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-8A) (Sl. No. 14) |  | Junior Engineer | ORD/000633/2022-2023 | 192/KSD | 24/05/2022 | 08/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.46 | 3.32 | 95.96 | 0
3 | BANKURA |  | Bankura Division | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VIII A WATER SUPPLY SCHEME | SM/16261 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 1.24 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VIII A WATER SUPPLY SCHEME | SM/16261 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000212/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 8.72 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VIII A WATER SUPPLY SCHEME | SM/16261 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone‐ VIII/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (SM/16261) |  |  | BILL/00660/2024-2025 |  | 09/08/2024 | 09/08/2024 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 13.33 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VIII A WATER SUPPLY SCHEME | SM/16261 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone‐ VIII/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (SM/16261) |  |  | BILL/01236/2024-2025 | BP-226/2024-25 | 13/08/2024 | 13/08/2024 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 13.33 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VIII A WATER SUPPLY SCHEME | SM/16261 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone- VIII/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000097/2023-2024 | 1135/BQA | 15/05/2023 | 01/11/2025 | SWAPAN KUMAR UPADHYAY | 228.33 | 88.61 | 38.81 | 45
8 | BANKURA |  | Bankura Division | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VIII A WATER SUPPLY SCHEME | SM/16261 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 180 Cum., staging height 20 Mtr.) including by pass arrangement and boundary wall with other allied works for Augmentation of Mukutmanipur, Khatra & Ranibundh Zone- VIII/A Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001768/2024-2025 | 491/BQA | 25/02/2025 | 26/10/2025 | TAPAN KUMAR MANDAL | 9.46 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VIII A WATER SUPPLY SCHEME | SM/16261 | Augmentation | Crossing of Road at different location by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Mukutmanipur, Khatra & Ranibundh (Zone- VIII/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000187/2024-2025 | 1859/BQA | 12/07/2024 | 26/08/2024 | M/S TARUN KUMAR PATRA | 13.69 | 0 | 0 | 100
Total | [13 empty] | 317.81 | 91.94 | 28.93