## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Barjora | Bankura Division | Ground Water Based Krishna Nagar (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | SM/16696 | New | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 2.61 | 0 | 0 | 0
2 | BANKURA | Barjora | Bankura Division | Ground Water Based Krishna Nagar (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | SM/16696 | New | Material Requisition To Resource Division |  |  | RTOR000066/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 5.21 | 0 | 0 | 0
3 | BANKURA | Barjora | Bankura Mechanical | Ground Water Based Krishna Nagar (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | SM/16696 | New | Ground Water Based Krishna Nagar (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. |  |  | BILL/00130/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.5 | 0 | 0 | 0
4 | BANKURA | Barjora | Bankura Division | Ground Water Based Krishna Nagar (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | SM/16696 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PROPOSED GROUND WATER BASED KRISHNANAGAR (MANACHAR) PIPED WATER SUPPLY SCHEME UNDER BANKURA SADAR SUB- DIVISION OF BANKURA DIVISION P.H.E. DTE. BLOCK- BARJORA, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000442/2023-2024 | 2276/BQA | 01/08/2023 | 27/04/2024 | PRAVAT SARKAR | 455.89 | 0 | 0 | 5
5 | BANKURA | Barjora | Bankura Mechanical | Ground Water Based Krishna Nagar (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | SM/16696 | New | Acceptance cum Formal work order for the work of Providing and installation of Low Lift pumping machineries and other electromechanical accessories for Ground water based Krishnanagar (Manachar) piped water supply scheme under Bankura Mechanical Division, P.H.E Dte.Block Barjora Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000578/2024-2025 | 1400/BMD | 12/12/2024 | 11/04/2025 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 39.35 | 0 | 0 | 0
6 | BANKURA | Barjora | Bankura Division | Ground Water Based Krishna Nagar (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | SM/16696 | New | Soil Investigation work for Construction and commissioning of R.C.C Over Head Reservoir (Intze type with solid raft) of capacity 250 cum and staging height 20 mtr as per approved drawing (No:-PC-I/OHR/10/2012) in connection with Jal Jeevan Mission (JJM) for Proposed Ground Water Based Krishnanagar (Manachar) PIped Water Supply Scheme under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block- Barjora, District -Bankura . Name of Muza - Paharpur (50%), Krishnanagar (50%) & Bamandihi (50%) | Assistant Engineer | Junior Engineer | ORD/000634/2022-2023 | 573/BQA | 17/03/2023 | 01/04/2023 | MS G. MITRA AND ASSOCIATES | 0.68 | 0 | 0 | 100
7 | BANKURA | Barjora | Bankura Division | Ground Water Based Krishna Nagar (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | SM/16696 | New | Preparation of piped network system & design the same including Route Survey using DGPS & all related failed work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS for Paharpur [Part] (JL No- 51), Krishnagar [Part] (JL No- 52) & Bamandihi [Part] (JL No- 54) mouza under Barjora Block all complete in consultation with PHED Planning Wings and clearance from SLSSC under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. |  |  | ORD/001186/2022-2023 | 354\BSD | 12/04/2022 | 27/04/2022 | M/S. R. DUTTA & CO. | 4.54 | 0 | 0 | 95
8 | BANKURA | Barjora | Bankura Division | Ground Water Based Krishna Nagar (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | SM/16696 | New | Material Requisition To Resource Division |  |  | RTOR000217/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 5.21 | 0 | 0 | 0
9 | BANKURA | Barjora | Bankura Division | Ground Water Based Krishna Nagar (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | SM/16696 | New | Material Requisition To Resource Division |  |  | RTOR000004/2024-2025 | 1736/BQA | 05/07/2024 | 05/07/2024 | Resource Division | 40.77 | 0 | 0 | 0
10 | BANKURA | Barjora | Bankura Mechanical | Ground Water Based Krishna Nagar (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | SM/16696 | New | Service connection charge for Krishnanagar (Manachar) water supply scheme Barjora block under BMD,PHE Dte.(SM/16696 ) |  |  | BILL/01097/2024-2025 | BP-2024-25-253 | 25/10/2024 | 25/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 13.35 | 0 | 0 | 0
Total | [13 empty] | 570.12 | 0 | 0