## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Barjora | Bankura Division | Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | SM/16697 | New | Preparation of piped network system & design the same including Route Survey using DGPS & all related failed work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS for Purokonda [Part] (JL No- 55), Tajpur [Part] (JL No- 56), Pakhanna- Bhairabpur [Part] (JL No- 57), Pakhanna [Part] (JL No- 58), Gopalpur [Part] (JL No- 59) & Radhakantapur [Part] (JL No- 60) mouza under Barjora Block all complete in consultation with PHED Planning Wings and clearance from SLSSC under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. |  |  | ORD/001187/2022-2023 | 355\BSD | 12/04/2022 | 27/04/2022 | LEMNISCATE | 4.25 | 4.25 | 100 | 95
2 | BANKURA | Barjora | Bankura Mechanical | Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | SM/16697 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for proposed ground water based Pakhanna( Manachar) piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Barjora Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000447/2023-2024 | 1775/BMD | 01/08/2023 | 30/09/2023 | TAPAN KUMAR SARKAR | 35.18 | 15.54 | 44.18 | 45
3 | BANKURA | Barjora | Bankura Division | Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | SM/16697 | New | Supply , Delivery, Construction , Commissioning and completion of all Civil works including all allied, related and enabling works for Proposed Ground Water Based Pakhanna (Manachar) Piped Water Supply Scheme under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block- Barjora, District -Bankura . Name of Mouza - Purokonda (50%), Tajpur (50%), Pakhanna Bhairabpur (50%), Pakhanna (50%), Gopalpur (50%), & Radhakantapur (50%) under JJM including Trial run for 3 months and O&M for a period of 3 years under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000433/2023-2024 | 2267/BQA | 01/08/2023 | 27/04/2024 | MD. AAMIR KHAN | 397.46 | 34.13 | 8.59 | 26
4 | BANKURA | Barjora | Bankura Division | Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | SM/16697 | New | Soil Investigation work for construction of OHR (200 CUM CAPACITY) under Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000898/2023-2024 | 3049/BQA | 06/11/2023 | 06/12/2023 | K S GROUP | 0.58 | 0 | 0 | 100
5 | BANKURA | Barjora | Bankura Division | Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | SM/16697 | New | Material Requisition To Resource Division |  |  | RTOR000039/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 1.79 | 0 | 0 | 0
6 | BANKURA | Barjora | Bankura Division | Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | SM/16697 | New | Material Requisition To Resource Division |  |  | RTOR000067/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 4.56 | 0 | 0 | 0
7 | BANKURA | Barjora | Bankura Mechanical | Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | SM/16697 | New | Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. |  |  | BILL/00131/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0 | 0
8 | BANKURA | Barjora | Bankura Division | Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | SM/16697 | New | Construction of Boundary wall in connection with Jal Jeevan Mission (JJM) for Proposed Ground Water Based Pakhanna (Manachar) PIped Water Supply Scheme under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block- Barjora, District -Bankura . Name of Muza - Purokonda (50%), Tajpur (50%), Pakhanna Bhairabpur (50%), Pakhanna (50%), Gopalpur (50%), & Radhakantapur (50%)., (Total Length:- 140mtr.). | Assistant Engineer | Junior Engineer | ORD/000199/2024-2025 | 1871/BQA | 12/07/2024 | 30/07/2026 | M/S SUPRIYA CHATTERJEE | 16.18 | 0 | 0 | 0
9 | BANKURA | Barjora | Bankura Mechanical | Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | SM/16697 | New | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electromechanical acessories at OHR site of Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | Assistant Engineer | Junior Engineer | ORD/000579/2024-2025 | 1402/BMD | 12/12/2024 | 11/04/2025 | SK ENTERPRISE | 30.4 | 0 | 0 | 0
10 | BANKURA | Barjora | Bankura Division | Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | SM/16697 | New | Construction of Guard room at OHR site in connection with Jal Jeevan Mission (JJM) for Proposed Ground Water Based Pakhanna (Manachar) PIped Water Supply Scheme under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block- Barjora, District -Bankura . Name of Muza - Purokonda (50%), Tajpur (50%), Pakhanna Bhairabpur (50%), Pakhanna (50%), Gopalpur (50%), & Radhakantapur (50%). | Assistant Engineer | Junior Engineer | ORD/001118/2024-2025 | 2974/BQA | 26/11/2024 | 24/02/2025 | SOMA BANERJEE | 4.58 | 0 | 0 | 100
11 | BANKURA | Barjora | Bankura Division | Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | SM/16697 | New | Material Requisition To Resource Division |  |  | RTOR000218/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 4.56 | 0 | 0 | 0
12 | BANKURA | Barjora | Bankura Mechanical | Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | SM/16697 | New | WBSEDCL Service connection charge for Pakhanna (Manachar) water supply scheme Barjora block under BMD,PHE Dte.(SM/16697) |  |  | BILL/01095/2024-2025 | BP-2024-25-252 | 25/10/2024 | 25/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 15.86 | 0 | 0 | 0
Total | [13 empty] | 517.4 | 53.92 | 10.42