## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Kotulpur | Bankura Division | Gopalpur Piped Water Supply Scheme. | SM/16698 | New | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 98.39 | 0 | 0 | 0
2 | BANKURA | Kotulpur | Bankura Mechanical | Gopalpur Piped Water Supply Scheme. | SM/16698 | New | Gopalpur |  |  | BILL/01504/2023-2024 | BP-2023-24-94 | 29/02/2024 | 29/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.11 | 0 | 0 | 0
3 | BANKURA | Kotulpur | Bankura Mechanical | Gopalpur Piped Water Supply Scheme. | SM/16698 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Gopalpur piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Kotulpur , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000172/2023-2024 | 885/BMD | 04/05/2023 | 01/04/2025 | ORIENTAL ENGINEERING CO. | 40.24 | 0 | 0 | 36
4 | BANKURA | Kotulpur | Bankura Division | Gopalpur Piped Water Supply Scheme. | SM/16698 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GOPALPUR PIPED WATER SUPPLY SCHEME, BLOCK- KOTULPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000470/2023-2024 | 2325/BQA | 14/08/2023 | 04/02/2025 | GOPAL CHANDRA CHOWDHURY | 598.08 | 0 | 0 | 70
Total | [13 empty] | 740.81 | 0 | 0