## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Patrasayer | Bankura Division | Bhubut Piped Water Supply Scheme | SM/16700 | New | Material Requisition To Resource Division |  |  | RTOR000020/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 22.5 | 0 | 0 | 0
2 | BANKURA | Patrasayer | Bankura Division | Bhubut Piped Water Supply Scheme | SM/16700 | New | Instalation of scheme information board for 2 nos. sites of Bhubut Piped Water Supply Scheme (SM/16700), 2 nos. sites of Kaktia Piped Water Supply Scheme (SM/16701) & 2 nos. sites of Karajbani Piped Water Supply Scheme (SM/16702) within Patrasayer Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001886/2024-2025 | 564/VSD | 27/09/2024 | 12/10/2024 | PARTHA ROY | 0.9 | 0 | 0 | 0
3 | BANKURA | Patrasayer | Bankura Mechanical | Bhubut Piped Water Supply Scheme | SM/16700 | New | New service connection for Bhubut (T/W-I) water supply scheme at Patrasayer block under BMD PHE Dte.(SM/16700) |  |  | BILL/01465/2024-2025 | BP-2024-25-363 | 07/02/2025 | 07/02/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.02 | 0 | 0 | 0
4 | BANKURA | Patrasayer | Bankura Mechanical | Bhubut Piped Water Supply Scheme | SM/16700 | New | New service connection for Bhubut water supply scheme (T/W-II) at Patrasayer block under BMD PHE Dte.(SM/16700) |  |  | BILL/01237/2024-2025 | BP-2024-25-312 | 16/12/2024 | 16/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.98 | 0 | 0 | 0
5 | BANKURA | Patrasayer | Bankura Division | Bhubut Piped Water Supply Scheme | SM/16700 | New | Supply, delivery, construction, commissioning and completion of all civil works including all allied, related and enabling works for Bhubut piped water supply scheme, Block- Patrasayer, Dist- Bankura under JJM including trial run for 3 months and O&M for a period of 3 years under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000820/2023-2024 | 2929/BQA | 26/10/2023 | 27/05/2025 | SHYAMA PADA DUTTA | 349.06 | 143.01 | 40.97 | 95
6 | BANKURA | Patrasayer | Bankura Mechanical | Bhubut Piped Water Supply Scheme | SM/16700 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories for newly sunk TW No I and TW No II of Bhubut piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Patrashayar, Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000112/2024-2025 | 423/BMD | 27/06/2024 | 17/06/2026 | ABHIJIT MUKHERJEE | 51.08 | 22.44 | 43.93 | 52
Total | [13 empty] | 438.55 | 165.45 | 37.73