## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Patrasayer | Bankura Division | Kaktia Piped Water Supply Scheme. | SM/16701 | New | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 71.81 | 0 | 0 | 0
2 | BANKURA | Patrasayer | Bankura Mechanical | Kaktia Piped Water Supply Scheme. | SM/16701 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories for newly sunk TW No I, TW No II, TW No III of Kaktia Piped water supply scheme Block Patrashayar under Bankura Mechanical Division, PHE Dte. Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000115/2024-2025 | 426/BMD | 27/06/2024 | 22/06/2025 | EASTERN INDIA SALES & SERVICE | 74.66 | 0 | 0 | 50
3 | BANKURA | Patrasayer | Bankura Mechanical | Kaktia Piped Water Supply Scheme. | SM/16701 | New | New Service connection at Kaktia water supply scheme near football ground at Patrasayer block under BMD PHE Dte.(SM/16701) |  |  | BILL/01355/2024-2025 | BP-2024-25-345 | 13/01/2025 | 13/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.34 | 0 | 0 | 0
4 | BANKURA | Patrasayer | Bankura Division | Kaktia Piped Water Supply Scheme. | SM/16701 | New | Restoration work of both side of road Habibpuskarini to Chakpatrasayer (WB-03-ADB12) of Length 365.00 Mtr. due to laying of pipeline of Kaktia PWSS [SM/16701] by Bankura Division. PHE Dte. |  |  | BILL/02019/2024-2025 |  | 25/03/2025 | 25/03/2025 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 3.91 | 0 | 0 | 0
5 | BANKURA | Patrasayer | Bankura Mechanical | Kaktia Piped Water Supply Scheme. | SM/16701 | New | New service connection for Kakatia Near Baura Para (SM/16701)water supply scheme at Patrasayer block under BMD PHE Dte. |  |  | BILL/01175/2024-2025 | BP-2024-25-302 | 04/12/2024 | 04/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.8 | 0 | 0 | 0
6 | BANKURA | Patrasayer | Bankura Division | Kaktia Piped Water Supply Scheme. | SM/16701 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR KAKTIA PIPED WATER SUPPLY SCHEME, BLOCK- PATRASAYER, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000350/2023-2024 | 2023/BQA | 24/07/2023 | 01/10/2025 | BAJRANG ROAD CONSTRUCTION PRIVATE LIMITED | 631.34 | 136.08 | 21.55 | 60
7 | BANKURA | Patrasayer | Bankura Mechanical | Kaktia Piped Water Supply Scheme. | SM/16701 | New | New service connection for Kakatia water supply scheme(SM/16701) in Patrasayer block under BMD PHE Dte. |  |  | BILL/02101/2024-2025 |  | 09/01/2025 | 09/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.8 | 0 | 0 | 0
Total | [13 empty] | 794.66 | 136.08 | 17.12