## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Patrasayer | Bankura Division | Kaktia Piped Water Supply Scheme. | SM/16701 | New | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 71.81 | 0 | 0 | 0
2 | BANKURA | Patrasayer | Bankura Division | Kaktia Piped Water Supply Scheme. | SM/16701 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR KAKTIA PIPED WATER SUPPLY SCHEME, BLOCK- PATRASAYER, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000350/2023-2024 | 2023/BQA | 24/07/2023 | 01/10/2025 | BAJRANG ROAD CONSTRUCTION PRIVATE LIMITED | 631.34 | 136.08 | 21.55 | 60
3 | BANKURA | Patrasayer | Bankura Mechanical | Kaktia Piped Water Supply Scheme. | SM/16701 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories for newly sunk TW No I, TW No II, TW No III of Kaktia Piped water supply scheme Block Patrashayar under Bankura Mechanical Division, PHE Dte. Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000115/2024-2025 | 426/BMD | 27/06/2024 | 22/06/2025 | EASTERN INDIA SALES & SERVICE | 74.66 | 0 | 0 | 50
Total | [13 empty] | 777.81 | 136.08 | 17.5