## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Patrasayer | Bankura Division | Karajbani Piped Water Supply Scheme | SM/16702 | New | Material Requisition To Resource Division |  |  | RTOR000050/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 23.46 | 0 | 0 | 0
2 | BANKURA | Patrasayer | Bankura Mechanical | Karajbani Piped Water Supply Scheme | SM/16702 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories for newly sunk TW No I and TW No II of Karajbani piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Patrashayar, Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000116/2024-2025 | 427/BMD | 27/06/2024 | 22/02/2025 | GOENKA ENTERPRISE | 51.06 | 0 | 0 | 21
Total | [13 empty] | 74.52 | 0 | 0